## Slide 1
Pacific Islands Ridge to Reef National Priorities – Integrated water, land, forest and coastal management to preserve biodiversity, ecosystem services, store carbon, improve climate resilience and sustain livelihoods
Second RSTC Technical Consultation, Radisson Blu Resort, Denarau, Fiji, February 17, 2020
Session 2: National R2R Demonstrations
IW R2R National Demonstrations – An update

## Slide 2
Unlikely implementation of consultancy for assessment and management plan within lifetime of project.
Local procurement process has taken over 4 months to recruit local consultants.
Fiji – 500 ha of catchment protect measures (Waimanu Catchment Management Plan)

## Slide 3
Unlikely going to have full impact known within life of this project
Local procurement process has taken over 4 months to recruit local consultants.
However, reported reduction of effluents due to DLT & there are plans to establish another one in the same area
Federated States of Micronesia – 200 ha of catchment protect measures (Tofol Integrated Catchment Management Plan)
Notes: Just like Fiji
Just like Fiji
However….

## Slide 4
Currently engaging local consultant on design of DLT pig pens
Environmental monitoring plan for monitoring of bore holes and household wells.
Baseline data available and monitoring allows stress reduction contribution of R2R intervention
Currently slow progress to agree on design of DLT piggery units
Kiribati – 955 TN kg/yr reduction of municipal waste pollution (30 DLT piggery units)
Notes: /
/
And to minimize underground contamination.
At this stage, there appears to be slow progress on agreement of design and construct of DLT piggery units. This also means it is getting difficult to establish clear determination of realistic progress of project.

## Slide 5
Identification of sites for revegetation with endemic, salt and drought tolerant species.
Report made available but delays during reporting period
A lot of time appears to be spent on planning but little action on revegetation efforts
Nauru – 10 ha restored habitat (coastal revegetation)
Notes: Initial steps taken….
Relevant planning documents, policies and regulations collected that will be needed to assess priority areas for actions…..
And to minimize underground contamination.
At this stage, there appears to be slow progress on agreement of design and construct of DLT piggery units. This also means it is getting difficult to establish clear determination of realistic progress of project.

## Slide 6
Ongoing effort to develop concept note for protection of water quality and supply from climate change impacts
Slow progress – focus on planning and minimal action.
No serious activities have commenced that help stress reduction measures and ICM planning for 200 ha.
Unless quick turnaround, unlikely to meet above target.
Niue – 200 ha catchment protection measures (ICM planning)

## Slide 7
Conservation and Protection Agency (CEPA) seeking potential donors/partners to advance implementation of Bootless Bay National Marine Sanctuary Management Plan for the next 5 years
Activities largely completed including policies and bylaws left to complete
Papua New Guinea – 13,867 ha (ICM planning)
Notes: A total of 13,867 ha of terrestrial and marine areas comprising of mangroves, estuaries, grassland,
rocky shores and sea areas covering seagrass, mudflats and reefs have been secured under the
Bootless Bay National Marine Sanctuary

## Slide 8
IW R2R RMI project initating meeting with potential consultant related to ICM plan work in Laura
Unless there is change in current efforts to mobilise resources and project activities, actual protection measures would be somewhat beyond scope of project.
Republic of the Marshall Islands – 255 ha (ICM planning)

## Slide 9
Planning, RapCA are done and catchment measures are implemented.
Only Support from RPCU needed is to ascertain effectiveness of these measures.
Final assessment can be made from technical staff (USP, RPCU & MNRE
Samoa – 1648 ha restored habitat (revegetation)
Notes: Planting of vetiver grass, river cleaning, awareness campaign towards 1648 ha of revegetation

## Slide 10
Honiara Coastal Assessment Report and Integrated Catchment Plan for Mataniko are in their final draft stage.
Local consultants will be hired to do regionally-led activities on diagnostic and SAF.
Full impact and therefore achievements of stress reduction targets fully realized beyond life of the project.
Solomon Islands – 575 ha restored habitat (revegetation)
Notes: All technical streams of work have been completed and used in the preparation of the above policies.
/
Implementation of protection and management measures in above plans and policies already in motion.

## Slide 11
Honiara Coastal Assessment Report and Integrated Catchment Plan for Mataniko are in their final draft stage.
Local consultants will be hired to do regionally-led activities on diagnostic and SAF.
Full impact and therefore achievements of stress reduction targets fully realized beyond life of the project.
Solomon Islands – 575 ha restored habitat (revegetation)
Notes: All technical streams of work have been completed and used in the preparation of the above policies.
/
Implementation of protection and management measures in above plans and policies already in motion.

## Slide 12
3 out of 6 planned household sanitation systems converted to compost toilets close to completion.
ICM planning closed to finish and activity jointly prepared with Ministry of Fisheries
All the above efforts work towards achieving SRTs, but also respond to domestic development priorities.
Tonga – 104 TN/kg/yr municipal waste reduction (revegetation); 90 ha conserved/protected (ICM plan)
Notes: In addition, parliament passing of the Water Resources Bill 2020 in which IW R2R Tonga contributed to its
Awareness
Upon media coverage in Q2 of the IW R2R
Tonga project, particularly a water quality test which showed E. coli presence in the water, this
awareness led to consultation from the public and decisions to be made regarding the passing of
the bill.

## Slide 13
Actual interventions are done. Only issue being the achieved SRTs will be fully realized at project closure.
Project currently progressing work to hire local consultants to do diagnostic analyses and SAF. The fee levels appear to be a contributing factor.
Vanuatu – 30 ha restored habitat (planting of endemic species); 2570 ha restored habitat (revegetation)
Notes: - Vanuatu is one of the sites where actual interventions (revegetation, restoration/reforestation) are
done.
- The only issue here whether the target of 2570 and 20 hectares are achieved until project is
closed.
-/

## Slide 14
Pacific Islands Ridge to Reef National Priorities – Integrated water, land, forest and coastal management to preserve biodiversity, ecosystem services, store carbon, improve climate resilience and sustain livelihoods
VINAKA
THANK YOU VERY MUCH
Presented by:
Presentation prepared by: John Carreon
Photo credits
Layout Navneet Lal, Graphics and multimedia assistant
Template: Shaleh Antonio, CCMEA
References:
…
Notes: In consideration of the uniqueness of the aspects of each IW R2R project demonstrations
implementation period, the successes and setbacks in achieving stress reduction targets provide the
RSTC Technical Consultation the opportunity to provide constructive, strategic and advice for the
remainder of the implementation period.