## Component 1
Capacity Building
Component | Outcomes | Activities | Source of Verification | Produced
1. Local capacity for waste management implementation and environmental protection built to enable best practice in coastal waters, land and public health protection | 1.1 Enabled Muri Community Motivation | 1.1.1.1 Working with other organisations to identify needs for environmental awareness | Awareness activities reported in project quarterly reports | K.1.1.1.1 Communications Strategy
1.1.1.2 Implementation of outreach and communications strategy including participation of Muri management
| 1.2 Muri Community Mobilised for ICM | 1.2.1.1 Identification of priority areas for community action for Muri Environment Care Group | Quarterly reports of network meetings and activities (including list of participants and results of work) Reports on lagoon issues | K.1.2.1.1 Identification of criteria for prioritisation of areas for community action for Muri Care
K.1.2.2.1 Standardised presentation for priority area for community action
| 1.3 National uptake of sustainable pig waste management methods stimulated through community awareness and training | 1.3.1.1 Work with regulating Ministry on a commercial piggery sewage management policy and Cabinet Submission | Consultation meeting minutes taken and reported on. | K.1.3.1.1 Commercial Piggery Sewage Management Policy
1.3.1.2 Ministry of Health to submit to Cabinet
Note on E5: Jaime Short: Beach stabilisation Drainage management

## Component 2
Public Private Partnership
Component | Outcomes | Activities | Source of Verification | Produced
2. Establishing public-private partnerships for tourism sector investment in ICM in Muri | 2.1 Cross-sectoral coordination established to explore the feasibility of public-private partnerships for tourism sector investment in ICM in Muri | 2.1.1.1 Consult with Cook Islands Investment Corporation on current project on PPP's | EIB Terms of Reference and membership lists, meeting reports, feasibility studies, desk-top reviews | K.2.1.2.1 Recommendation for PPP's for tourism sector investment in ICM in Muri
2.1.2.1 Muri Care Partnership formalised
| 2.2 Accepted mechanisms for public-private partnerships for the tourism sector in ICM established | 2.2.1.1 Consult with tourism operators and applicable stakeholders (including Tourism Cook Islands Green Accrediation Scheme) on viable meausres for ICM | Guidelines on establishing public-private partnerships for tourism sector investment in ICM | K.2.2.1.1 Review National and Regional public-private partnership arrangements Report
|  | 2.2.1.2 Develop guidelines for public-private partnerships for the tourism sector in ICM |  | K.2.2.1.2 Guidelines for public-private partnerships for the tourism sector in ICM
2.2.1.3.Seek endorsement from Public and Private ICM stakeholders.
| 2.3 Public-private partnerships for tourism sector investment in ICM established for enhanced environmental protection in Muri | 2.3.1.1 Seek partnerships with tourism operators | Tourism sector and community consultation documents, PPP agreements and plans | K.2.3.1.1 Agreements signed
2.3.1.3 Public-private partnerships for tourism sector formalised
Note on E5: Jaime Short: Currently being done under CIIC
Note on E6: Jaime Short: BTIB link
Note on B8: Jaime Short: (Muri Environment Care project - Nukupure Beach Coastal Protection Project) (Target Nautilus, Muri Beachcomber and Pacific Resort for supporting riparian planting along their stream and lowland areas,promoting habitat conservation, attenuation for stormwater and keeping drainage channels on their properties maintained).
Note on C8: Jaime Short: Green Accreditation
Note on C9: Jaime Short: Finance repairs Obligation to plant foreshore use Nautilus as a model Agreements not to put any more hard engineering shore front protection in

## Component 3
Increase knowledge and management
Components | Outcomes | Activities | Source of Verification | Produced
3. Increasing knowledge-base and capacity for effective environmental stress reduction measures and integrated catchment management in Muri | 3.1 Ecological health of Muri Lagoon characterised and land-based contamination processes established for key ICM planning and investment | 3.1.1.1 Conduct RAPCA | Planning meeting minutes, photos, RAPCA report | K. 3.1.1.1 RAPCA report
|  | 3.1.1.2 Obtain infromation on contamination processes and sources for key ICM planning and investment | Mei Te Vai Ki Te Vai Project environmental investigations | K. 3.1.1.2 Endorsed Mei Te Vai environmental investigation report
|  | 3.1.1.3 Develop R2R planning response to address and mitigate contaminants and likely investment impacts | Meeting minutes, sources for information, contracts for procured services | K.3.1.1.3 Draft erosion and sediment control standards with accompanying guide for contractors.
| 3.2 Increased local community for understanding the development process | 3.2.1.1 Conduct gap analysis on development process | Contracted services for gap analysis and development of booklet. | K.3.2.1.1 A published booklet on Permits and Consents process with tips on sustainable development
| 3.3 Improved integrated catchment management via monitoring and evaluation of existing stress reduction measures | 3.3.1.1 Identify one focus area for a pilot site for demonstrating a stress reduction measure | Contracted services for feasibility on reducing the stress | K.3.2.1.1 Feasibility assessment with developed design.
|  | 3.3.1.2 Develop an information base of land features | Contracted or agreed services for GeoMap development | K.3.2.1.2 GeoMap created for the Cook Islands
Note on C9: Jaime Short: The stress is stormwater