## Original (hidden)
Detailed Work and Financial Plan
Project Title:
Recipient:
Implementation Period:
Version:
Reference No. |  |  | Output/ Major activity/ Sub activity | Quantity | Unit of Measure | Unit price | Detailed components of the unit price | [6 empty] | Cost per output and activity | Fund Sources |  |  |  | Period Coverage | [35 empty] | Responsible Party |  |  | REMARKS
[7 empty] | Personnel/ Consultant/s (Person x Daily Rate x Days) | Estimated Travel & Accomm Cost | Workshop venue | Food | Procurement or rental of Equipments, materials, publication, etc. | Others | Subtotal Cost per unit |  | National Budget | SPC-R2R | Others | Total Budget (in FJD) | 2018 | [11 empty] | 2019 | [11 empty] | 2020
[19 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | Main/Lead | Support | Others
1 |  |  | Appropriate onsite pig waste management piloted | 1 | 0 | 4350 | 2400 | 900 | 500 | 500 | 50 | 0 | 4350 | 4350 | 0 | 0 | 0 | 0 | bar: 2018 J
| 1 |  |  | 1 |  | 4350 | 2400 | 900 | 500 | 500 | 50 | 0 | 4350 | 4350 | 0 | 0 | 0 | 0 | bar: 2018 J to 2018 A
|  | 1 | Assessment of Pig Waste impacts and management practices. | 1 | District or area | 2100 | 1400 | 700 | 0 | 0 | 0 | 0 | 2100 | 2100 |  |  |  | 0 | bar: 2018 J to 2018 M
|  | 2 | Review pig waste management options, include cost considerations | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  | 0 | bar: 2018 F to 2018 M
|  | 3 | Consult, design and construct X number of improved domestic pig pen. (dry litter) | 1 | District or area | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 600 |  |  |  | 0 | bar: 2018 A
|  | 4 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
|  | 5 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
| 2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2018 A to 2018 J
|  | 1 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 |  |  |  | 0 | bar: 2018 A
|  | 2 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 |  |  |  | 0 | bar: 2018 A to 2018 M
|  | 3 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 |  |  |  | 0 | bar: 2018 M
|  | 4 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0 | bar: 2018 J
2 |  |  | State of the Cost Report available | 1 | SCR Report | 7005 | 3800 | 1100 | 1000 | 1000 | 105 | 0 | 7005 | 7250 | 0 | 0 | 0 | 0 | bar: 2018 J
| 1 |  |  | 1 | SCR Report | 4350 | 2400 | 900 | 500 | 500 | 50 | 0 | 4350 | 4350 | 0 | 0 | 0 | 0 | bar: 2018 J to 2018 A
|  | 1 | 1.2.1.1 Assessment of baseline nutrient and pathogen loads from current pig waste management practices | 1 | District or area | 2100 | 1400 | 700 | 0 | 0 | 0 | 0 | 2100 | 2100 |  |  |  | 0 | bar: 2018 J to 2018 M
|  | 2 | 1.2.1.2 Monitoring program inititated with construction of improved domestic pig pen | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  | 0 | bar: 2018 F to 2018 M
|  | 3 | 1.2.1.3 Assessment of reduction in nutrient and pathogen loads from improved domestic pig waste management practices | 1 | District or area | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 600 |  |  |  | 0 | bar: 2018 A
|  | 4 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
|  | 5 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
| 2 |  | Packgaging of the State of the Cost Report (SCR) | 1 | SCR Report | 2655 | 1400 | 200 | 500 | 500 | 55 | 0 | 2655 | 2900 | 0 | 0 | 0 | 0 | bar: 2018 A to 2018 J
|  | 1 | Drafting of the SCR | 1 | SCR Report | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 700 |  |  |  | 0 | bar: 2018 A
|  | 2 | Conduct validation meetings on the biodiversity assessment results | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  | 0 | bar: 2018 A to 2018 M
|  | 3 | Revision/editing, finalization of the SCR | 1 | SCR Report | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 300 |  |  |  | 0 | bar: 2018 M
|  | 4 | Publication of the SCR | 50 | copies | 5 | 0 | 0 | 0 | 0 | 5 |  | 5 | 250 |  |  |  | 0 | bar: 2018 J
3 |  |  | State of the Cost Report available | 1 | SCR Report | 7005 | 3800 | 1100 | 1000 | 1000 | 105 | 0 | 7005 | 7250 | 0 | 0 | 0 | 0 | bar: 2018 J
| 1 |  | Conduct of biodiversity assessment survey | 1 | SCR Report | 4350 | 2400 | 900 | 500 | 500 | 50 | 0 | 4350 | 4350 | 0 | 0 | 0 | 0 | bar: 2018 J to 2018 A
|  | 1 | Conduct data collection and occular inspection | 1 | District or area | 2100 | 1400 | 700 | 0 | 0 | 0 | 0 | 2100 | 2100 |  |  |  | 0 | bar: 2018 J to 2018 M
|  | 2 | Conduct consultation meetings | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  | 0 | bar: 2018 F to 2018 M
|  | 3 | Perform data consolidation, analysis and interpretation | 1 | District or area | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 600 |  |  |  | 0 | bar: 2018 A
|  | 4 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
|  | 5 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
| 2 |  | Packgaging of the State of the Cost Report (SCR) | 1 | SCR Report | 2655 | 1400 | 200 | 500 | 500 | 55 | 0 | 2655 | 2900 | 0 | 0 | 0 | 0 | bar: 2018 A to 2018 J
|  | 1 | Drafting of the SCR | 1 | SCR Report | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 700 |  |  |  | 0 | bar: 2018 A
|  | 2 | Conduct validation meetings on the biodiversity assessment results | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  | 0 | bar: 2018 A to 2018 M
|  | 3 | Revision/editing, finalization of the SCR | 1 | SCR Report | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 300 |  |  |  | 0 | bar: 2018 M
|  | 4 | Publication of the SCR | 50 | copies | 5 | 0 | 0 | 0 | 0 | 5 |  | 5 | 250 |  |  |  | 0 | bar: 2018 J
4 |  |  | State of the Cost Report available | 1 | SCR Report | 7005 | 3800 | 1100 | 1000 | 1000 | 105 | 0 | 7005 | 7250 | 0 | 0 | 0 | 0 | bar: 2018 J
| 1 |  | Conduct of biodiversity assessment survey | 1 | SCR Report | 4350 | 2400 | 900 | 500 | 500 | 50 | 0 | 4350 | 4350 | 0 | 0 | 0 | 0 | bar: 2018 J to 2018 A
|  | 1 | Conduct data collection and occular inspection | 1 | District or area | 2100 | 1400 | 700 | 0 | 0 | 0 | 0 | 2100 | 2100 |  |  |  | 0 | bar: 2018 J to 2018 M
|  | 2 | Conduct consultation meetings | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  | 0 | bar: 2018 F to 2018 M
|  | 3 | Perform data consolidation, analysis and interpretation | 1 | District or area | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 600 |  |  |  | 0 | bar: 2018 A
|  | 4 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
|  | 5 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
| 2 |  | Packgaging of the State of the Cost Report (SCR) | 1 | SCR Report | 2655 | 1400 | 200 | 500 | 500 | 55 | 0 | 2655 | 2900 | 0 | 0 | 0 | 0 | bar: 2018 A to 2018 J
|  | 1 | Drafting of the SCR | 1 | SCR Report | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 700 |  |  |  | 0 | bar: 2018 A
|  | 2 | Conduct validation meetings on the biodiversity assessment results | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  | 0 | bar: 2018 A to 2018 M
|  | 3 | Revision/editing, finalization of the SCR | 1 | SCR Report | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 300 |  |  |  | 0 | bar: 2018 M
|  | 4 | Publication of the SCR | 50 | copies | 5 | 0 | 0 | 0 | 0 | 5 |  | 5 | 250 |  |  |  | 0 | bar: 2018 J
5 |  |  | State of the Cost Report available | 1 | SCR Report | 7005 | 3800 | 1100 | 1000 | 1000 | 105 | 0 | 7005 | 7250 | 0 | 0 | 0 | 0 | bar: 2018 J
| 1 |  | Conduct of biodiversity assessment survey | 1 | SCR Report | 4350 | 2400 | 900 | 500 | 500 | 50 | 0 | 4350 | 4350 | 0 | 0 | 0 | 0 | bar: 2018 J to 2018 A
|  | 1 | Conduct data collection and occular inspection | 1 | District or area | 2100 | 1400 | 700 | 0 | 0 | 0 | 0 | 2100 | 2100 |  |  |  | 0 | bar: 2018 J to 2018 M
|  | 2 | Conduct consultation meetings | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  | 0 | bar: 2018 F to 2018 M
|  | 3 | Perform data consolidation, analysis and interpretation | 1 | District or area | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 600 |  |  |  | 0 | bar: 2018 A
|  | 4 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
|  | 5 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
| 2 |  | Packgaging of the State of the Cost Report (SCR) | 1 | SCR Report | 2655 | 1400 | 200 | 500 | 500 | 55 | 0 | 2655 | 2900 | 0 | 0 | 0 | 0 | bar: 2018 A to 2018 J
|  | 1 | Drafting of the SCR | 1 | SCR Report | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 700 |  |  |  | 0 | bar: 2018 A
|  | 2 | Conduct validation meetings on the biodiversity assessment results | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  | 0 | bar: 2018 A to 2018 M
|  | 3 | Revision/editing, finalization of the SCR | 1 | SCR Report | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 300 |  |  |  | 0 | bar: 2018 M
|  | 4 | Publication of the SCR | 50 | copies | 5 | 0 | 0 | 0 | 0 | 5 |  | 5 | 250 |  |  |  | 0 | bar: 2018 J
6 |  |  | State of the Cost Report available | 1 | SCR Report | 7005 | 3800 | 1100 | 1000 | 1000 | 105 | 0 | 7005 | 7250 | 0 | 0 | 0 | 0 | bar: 2018 J
| 1 |  | Conduct of biodiversity assessment survey | 1 | SCR Report | 4350 | 2400 | 900 | 500 | 500 | 50 | 0 | 4350 | 4350 | 0 | 0 | 0 | 0 | bar: 2018 J to 2018 A
|  | 1 | Conduct data collection and occular inspection | 1 | District or area | 2100 | 1400 | 700 | 0 | 0 | 0 | 0 | 2100 | 2100 |  |  |  | 0 | bar: 2018 J to 2018 M
|  | 2 | Conduct consultation meetings | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  | 0 | bar: 2018 F to 2018 M
|  | 3 | Perform data consolidation, analysis and interpretation | 1 | District or area | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 600 |  |  |  | 0 | bar: 2018 A
|  | 4 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
|  | 5 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
| 2 |  | Packgaging of the State of the Cost Report (SCR) | 1 | SCR Report | 2655 | 1400 | 200 | 500 | 500 | 55 | 0 | 2655 | 2900 | 0 | 0 | 0 | 0 | bar: 2018 A to 2018 J
|  | 1 | Drafting of the SCR | 1 | SCR Report | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 700 |  |  |  | 0 | bar: 2018 A
|  | 2 | Conduct validation meetings on the biodiversity assessment results | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  | 0 | bar: 2018 A to 2018 M
|  | 3 | Revision/editing, finalization of the SCR | 1 | SCR Report | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 300 |  |  |  | 0 | bar: 2018 M
|  | 4 | Publication of the SCR | 50 | copies | 5 | 0 | 0 | 0 | 0 | 5 |  | 5 | 250 |  |  |  | 0 | bar: 2018 J
7 |  |  | State of the Cost Report available | 1 | SCR Report | 7005 | 3800 | 1100 | 1000 | 1000 | 105 | 0 | 7005 | 7250 | 0 | 0 | 0 | 0 | bar: 2018 J
| 1 |  | Conduct of biodiversity assessment survey | 1 | SCR Report | 4350 | 2400 | 900 | 500 | 500 | 50 | 0 | 4350 | 4350 | 0 | 0 | 0 | 0 | bar: 2018 J to 2018 A
|  | 1 | Conduct data collection and occular inspection | 1 | District or area | 2100 | 1400 | 700 | 0 | 0 | 0 | 0 | 2100 | 2100 |  |  |  | 0 | bar: 2018 J to 2018 M
|  | 2 | Conduct consultation meetings | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  | 0 | bar: 2018 F to 2018 M
|  | 3 | Perform data consolidation, analysis and interpretation | 1 | District or area | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 600 |  |  |  | 0 | bar: 2018 A
|  | 4 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
|  | 5 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
| 2 |  | Packgaging of the State of the Cost Report (SCR) | 1 | SCR Report | 2655 | 1400 | 200 | 500 | 500 | 55 | 0 | 2655 | 2900 | 0 | 0 | 0 | 0 | bar: 2018 A to 2018 J
|  | 1 | Drafting of the SCR | 1 | SCR Report | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 700 |  |  |  | 0 | bar: 2018 A
|  | 2 | Conduct validation meetings on the biodiversity assessment results | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  | 0 | bar: 2018 A to 2018 M
|  | 3 | Revision/editing, finalization of the SCR | 1 | SCR Report | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 300 |  |  |  | 0 | bar: 2018 M
|  | 4 | Publication of the SCR | 50 | copies | 5 | 0 | 0 | 0 | 0 | 5 |  | 5 | 250 |  |  |  | 0 | bar: 2018 J
|  |  | Grand Total |  |  |  | 25200 | 7500 | 6500 | 6500 | 680 | 0 | 46380 | 47850 | 0 | 0 | 0 | 0

## Dashboard
Status of Implementation
Date Updated: |  | Nov. 6, 2018
Project Facts
| Project Facts | Quantity
| Component | 3
| Output | 0
| Major Activities | 0
| Sub-activities | 20
Outputs Produced
| Component | Number of Outputs | Completed | Ongoing | Not Yet Started
| Component 1 | #REF! | #REF! | #REF! | #REF!
| Component 2 | #REF! | #REF! | #REF! | #REF!
| Component 3 | #REF! | #REF! | #REF! | #REF!
| Component 4 | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
| Component | Number of Major Activities | Completed | Ongoing | Not Yet Started
| Component 1 | 0 | 0 | 0 | 0
| Component 2 | #REF! | #REF! | #REF! | #REF!
| Component 3 | #REF! | #REF! | #REF! | #REF!
| Component 4 | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
0
Project Summary:
4 Components
13 Outputs
33 Activities

## Multi-Year_IndicatorTracking
Achievement of Results
Project Title:
Implementing Partner:
Implementation Period:
Update as of: |  | 2018-05-27
Updated by: |  | ______________________________
Code | Project Component/ Objective Statement |  | Indicator | Baseline | Target End of Project | End of Project Target | End of Target Balance (Column G-(Column R) | Annual Planned Targets |  |  |  |  | Summary of the Actual Annual Achievements (As reported in the PIR) |  |  |  |  | Means/Source of Verification | Risks and Assumptions | REMARKS Strategic Requirements and Conditions for successful implementation, risks and assmptions monitoring, etc.
[8 empty] | 2017 | 2018 | 2019 | 2020 | Total (Equal to End of Project Target) | 2017 | 2018 | 2019 | 2020 | Total Accumulated Accomplishment (Final Report)
Project Objective Level
[7 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Outcome | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Output | 1.1.1 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 1.1.2 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.2 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Output | 1.2.1 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.3 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Output | 1.3.1 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 1.3.2 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
2.1 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Output | 2.1.1 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
2.2 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Output | 2.2.1 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 2.2.2. | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 2.2.3 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 2.2.4 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Outputs | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | 14 National pilot project area diagnostics based on R2R approach inclluding: baseline environmental state and social data incorporating CC vulnerabilities; and local governance of water, land, forests and coasts reviewed | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.2 | 14 national pilot projects test methods for catalizing local community action, utilizing and providing best practice examples, and building institutional linkages for integrated land, forest, water and coastal management | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
2.3 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Output | 2.3.1 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 2.3.2 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 2.3.3 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
3.1 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Output | 3.1.1 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 3.1.2 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 3.1.3 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
3.2 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Output | 3.2.1 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 3.2.2 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
3.3 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Output | 3.3.1 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 3.3.2 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 3.3.3 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | Reports on visits undertaken, both progress reports and those of participants | Demonstrable improved and results of best practices will only start to become evident towards the end of the project, including for LMMA, forest plantings and conservation farming/agroforestry practices

## MYCWP Kiribati
Multi-Year Costed Work Plan
Project Title: |  |  |  |  | Kiribati IW Ridge to Reef Project | [19 empty] | 0
Implementing Partner: |  |  |  |  | Environment and Conservatoin Division MELAD
Implementation Period: |  |  |  |  | March 2018 or January 2019 - June 2021 | [20 empty] | #DIV/0! | #DIV/0! |  | #DIV/0!
Version: |  |  |  |  | v5 5 November 2019 - approved at the 1st PSC meeting.61119
Reference Code |  |  |  |  | Output/ Major activity/ Sub activity | Status | Quantity | Unit of Measure | per unit price (usd) | Detailed Components of the unit price | [14 empty] | Total Cost for the activity (Column H multiply with Column X) | Fund Sources | [6 empty] | Implementation Period | [35 empty] | Responsible Parties |  |  | REMARKS
Component | Outcome | Output | Major Activity | Sub-Activity | [5 empty] | 71200 | 71300 | 71400 | 71600 | 72100 | 72200 | 72400 | 72500 | 72800 | 73400 | 74100 | 74200 | 74500 | 75700 | Subtotal Cost per unit |  | Government of Kiribati | National IW R2R Project | STAR Project | Regional R2R/SPC Funds | Others1 | Others2 | Total Budget (in USD) | 2019 | [11 empty] | 2020 | [11 empty] | 2021
[10 empty] | International Consultants | Local Consultants | Contractual Services - Individuals | Travel on Office Business | Contractual Services - Companies | Equipment & furniture | Comm. and Audio Visual equipment | Supplies | Information technology equipment | Rental & Maintenance of other equipment | Professional Services | Audio Visual & Printing Production Costs | Miscellaneous expenses | Training, Worskshops & Conferences | [9 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Main/Lead | Support | Others
[5 empty] | Project Management Unit | [27 empty] | 2019 Jan: 0
|  | 1 |  |  | Establishment of Project Management Unit | [18 empty] | 0 | 0 | [6 empty] | 0 | bar: 2019 Sept to 2021 Jun
|  |  | 1 |  | Advertisement of the vacancy for project personnel |  | 5 | TOR and advertisement (announcements, newspaper) | 400 |  |  | 400 | [11 empty] | 400 | 2000 |  | 2000 |  |  |  |  | 2000 | [36 empty] | Director & Senior Staffs | RPCU |  | radio and newsletter, online advertisements (Env website, etc.)
|  |  | 2 |  | Project Personnnel (Remuneration = Salary + Benefits) | 1 | 18 | monthly Salary | 3800 |  |  | 3800 | [11 empty] | 3800 | 68400 |  | 68400 |  |  |  |  | 68400 | [36 empty] | Project Manager | Project Assistants | DoE & Senior Officials, RPCU | Project Manager, Part-time Assistants
|  | 2 |  |  | Project Operations | 1 |  |  | 0 | [14 empty] | 0 | 0 | [6 empty] | 0 | bar: 2019 Oct to 2021 Jun
|  |  | 1 |  | Communication (Internet) | 1 | 18 | monthly | 300 | [6 empty] | 300 | [7 empty] | 300 | 5400 | 5000 | 400 |  |  |  |  | 5400 | [36 empty] | Project Manager | Project Assistants | DoE & Senior Officials, RPCU | largely Kiribati Govt in-kind contributions; project contributions relatively small | bar: 2019 Oct to 2021 Jun
|  |  | 2 |  | Office Space (Including Utilities) | 1 | 18 | monthly | 250 |  |  | 250 | [11 empty] | 250 | 4500 | 4500 | [5 empty] | 4500 | [36 empty] | Project Manager | Project Assistants | DoE & Senior Officials, RPCU | largely Kiribati Govt in-kind contributions; project contributions relatively small | bar: 2019 Oct to 2021 Jun
|  |  | 3 |  | Supplies (Ink Cartridges, Papers, etc.) | 1 | 18 | monthly | 500 |  |  | 500 | [11 empty] | 500 | 9000 | 3000 | 6000 |  |  |  |  | 9000 | [36 empty] | Project Manager | Project Assistants | DoE & Senior Officials, RPCU | project cost mainly but also back-up support from govt | bar: 2019 Oct to 2021 Jun
|  |  | 4 |  | Attendance to RPSC Meetings (visa & other travel costs) | 1 | 2 | At Cost | 2000 | [10 empty] | 2000 |  |  |  | 2000 | 4000 | 1000 |  | 1000 | 2000 |  |  | 4000 | [36 empty] | Project Manager | DoE | Permanent Secretary | RPCU costs; sometimes Kiribati govt send the 2 or third person at cost | bar: 2020 Jul; 2020 Dec
|  |  | 5 |  | Organise and facilitate IW (or Joint) R2R Project Steering Committee Meetings | 1 | 2 | Meeting agenda; list of participants and minutes including outcomes | 1000 | [13 empty] | 1000 | 1000 | 2000 | 500 | 1000 |  | 500 |  |  | 2000 | [36 empty] | Project Manager | Project Assistants | DoE & Senior Officials, RPCU | project cost mainly but also back-up support from govt | bar: 2019 Nov; 2020 Jun; 2020 Dec; 2021 Jun
|  |  | 6 |  | Office Equipment | 1 | 1 | office space (Env Office) | 16000 | [5 empty] | 15000 | [6 empty] | 1000 |  | 16000 | 16000 | 1000 | 15000 |  |  |  |  | 16000 | [36 empty] | Project Manager | Project Assistants | DoE & Senior Officials, RPCU | project cost mainly but also back-up support from govt | bar: 2019 Oct to 2021 Jun
|  |  | 7 |  | WQ equipment | 1 | 1 | equipment | 7890 | [5 empty] | 7890 | [8 empty] | 7890 | 7890 |  |  |  | 7890 |  |  | 7890 | [36 empty] | Project Manager | Project Assistants | DoE & Senior Officials, RPCU | RPCU costs | bar: 2019 Dec
|  |  | 8 |  | Preparation of Project Final Evaluation |  | 1 | report | 4300 |  |  | 4000 | 300 | [10 empty] | 4300 | 4300 | 300 | 3000 |  | 1000 |  |  | 4300 | [36 empty] | Project Manager | Project Assistants | DoE & Senior Officials, RPCU | RPCU costs | bar: 2020 Nov to 2020 Dec
|  |  |  | a | conduct constultations with stakeholders and community groups | 0 | 5 | consultation reports and media articles | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | b | Conduct field visitation; final environmental monitoring (link with 2.2) and prepare summary report | 0 | 1 | activity report and analysis report | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | c | prepare final evalutaion report | 0 | 1 | draft report | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | d | final evaluation report endorsed through Project Steering Committee | 0 | 1 | endorsed report | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  | 9 |  | Prepare Lessons Learned document as per RPSC4 or regional deliverables |  | 1 | final lessons learned document approved | 700 |  |  | 700 | [11 empty] | 700 | 700 | 200 |  |  | 500 |  |  | 700 | [36 empty] | Project Manager | DoE, Senior Staffs, | RPCU Comms | Staffs salaries, RPCU and in-kind contributions (Env staffs)
1 |  |  |  |  | Local capacity for sustainable piggery waste management stimulated through effective community engagement and training | 0 |  |  | 0 | [14 empty] | 0 | 0 | [6 empty] | 0
| 1 |  |  |  | Volunteer piggery waste management networks are formally established | 0 | [17 empty] | 0 | 0 | [6 empty] | 0
|  | 1 |  |  | Bonriki Waste Management Network TOR endorsed | 0 | [17 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | [36 empty] | Project Manager | EOU (Environment Awareness Unit of ECD), EH, Health Statistic, ALD | bar: 2020 Jan to 2020 Feb
|  |  | 1 |  | Stakeholder consultation for development of network | 0 | 5 | consultations | 600 |  |  | 200 |  | 300 | [8 empty] | 100 | 600 | 3000 | 250 | 1500 |  | 1250 |  | 0 | 3000
|  |  |  | 1 | Conduct meetings and consultations with community stakeholders to prepare concept and draft TOR | 0 |  | concept paper; community engagement and activity reports; draft TOR | [15 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0
|  |  | 2 |  | TOR for Waste Management Network prepared and endorsed by stakeholders and Project Steering committee | 0 | 1 | endorsed TOR | 400 |  |  | 400 | [11 empty] | 400 | 400 | 200 |  |  | 200 |  | 0 | 400 | [36 empty] | Project Manager | DoE, Env staffs | RPCU | no cost because the TOR will be developed by PM and assisted by Env senior staffs plus RPCU | bar: 2020 Feb
|  | 2 |  |  | Bonriki Waste Management Network operational | 0 | [17 empty] | 0 | 0 | [5 empty] | 0 | 0
|  |  | 1 |  | Inception meeting for Bonriki Waste Management Network | 0 | 1 | inception meeting agenda and minutes, signed MOA | 3800 |  | 1000 | 2800 | [11 empty] | 3800 | 3800 | 1000 | 1300 |  | 1500 |  | 0 | 3800 | [36 empty] | Project Manager | EOU, EH, Health Statistic, ALD, Mayors for pilote area | bar: 2020 Mar
|  |  |  | 1 | MOA with volunteers is signed | 0 |  | signed MOA | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  | 2 |  | outreach and training for network members, information exchange with wider community | 0 | 1 | outreach strategy, reports | 7000 |  | 2000 | 5000 | [11 empty] | 7000 | 7000 | 1000 | 5000 |  | 1000 |  | 0 | 7000 | [36 empty] | LC (Local Consultant) | Project Manager, ECD (EOU), | DoE & Senior Officials, RPCU | bar: 2020 Mar to 2020 Apr
|  |  |  | 1 | In association with 3.1 participate in development of community outreach Program | 0 | 1 | outreach strategy | [15 empty] | 0 | 0 | [5 empty] | 0 | 0
|  |  |  | 2 | Support and participate in community Outreach Program and monitor outcomes | 0 | 4 | activity & training workshop report | [15 empty] | 0 | 0 | [5 empty] | 0 | 0
| 2 |  |  |  | Improved donor support for increased householder uptake of sustainable piggery waste management | [18 empty] | 0 | 0 | [6 empty] | 0
|  | 1 |  |  | Sustainable options for financing documented and training delivered | 0 |  |  | 0 | [14 empty] | 0 | 0 | [6 empty] | 0 | bar: 2020 Apr to 2020 Jun
|  |  | 1 |  | Identify potential sustainable financing options for communties and HH and develop guidelines for financing | 0 | 1 | reports, minutes, activity notes, guidelines | 12500 |  | 4000 | 4000 |  |  |  |  | 1500 |  | 1000 |  |  |  | 2000 | 12500 | 12500 | 500 | 11000 |  | 1000 |  |  | 12500 | [36 empty] | Project Manager | RPCU, MELAD (ECD Management) | DoE & Senior Officials, RPCU
|  |  |  | 1 | Engage with financial institutions; research crowdfunding and donor or sponorship and identify opportunities and requirements | 0 |  | Meeting minutes; research notes | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 2 | Prepare summary report on findings with recommendations and guidance notes; include monitoring of uptake | 0 |  | Summary report | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 3 | Present final report to technical group and stakeholders for feedback | 0 |  | Feedback notes | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 4 | Incorporate feedback and submit final report to technical and steering committee for endorsement | 0 |  | Final report - endorsed | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 5 | Package and publish report and guidelines (RPCU to support) | 0 |  | Published report and guidelines | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  | 2 |  | As per the Outreach Program (3.1) deliver schedule of workshops accessing financing options. | 0 | 2 | reports, notes, media articles | 5500 |  | 1000 | 2000 | [10 empty] | 2500 | 5500 | 11000 | 1500 | 8000 |  | 1500 |  |  | 11000 | [36 empty] | LC (DLT) | ECD (EOU), RPCU | DoE & Senior Officials, RPCU | bar: 2020 May to 2020 Jul
|  |  |  | 1 | Engage with Waste Management Network and community to present the report and guidelines | 0 | 1 | activity and workshop reports | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 2 | Gather feedback on workshops and update accordingly | 0 | 1 | feedback forms and summary report | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 3 | Monitor and report on uptake of options in the guidelines as per the Outreach Program | 0 | 1 | report on uptake | [15 empty] | 0 | 0 | [6 empty] | 0
| 3 |  |  |  | National uptake of sustainable pig waste management methods stimulated through community awareness and training | [18 empty] | 0 | 0 | [6 empty] | 0
|  | 1 |  |  | Technical training workshops conducted | [18 empty] | 0 | 0 | [6 empty] | 0 | bar: 2020 Jul
|  |  | 1 |  | As per the Community Outreach Program (3.1) deliver schedule of workshops and training |  | 2 | reports, activity notes | 6000 |  | 2000 | 2000 |  |  |  |  | 500 |  | 500 |  |  |  | 1000 | 6000 | 12000 | 2000 | 8000 |  | 2000 |  |  | 12000
|  |  |  | 1 | Engage with Waste Management Network and identified partners to deliver training |  |  | workshop repotrs and consultation reports | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 2 | Gather feedback on workshops and update accordingly |  |  | participatory interviews | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 3 | Monitor and report on effectiveness of DLT training as per the Outreach Program |  |  | monitoring/evaluation reports | [15 empty] | 0 | 0 | [6 empty] | 0
2 |  |  |  |  | Demonstration of innovative approaches to pig waste management | 0 |  |  | 0 | [14 empty] | 0 | 0 | [6 empty] | 0
| 1 |  |  |  | Improved domestic pig pen operations catalysed via piloting of locally appropriate methods for on-site pig waste management | 0 | [17 empty] | 0 | 0 | [6 empty] | 0 | bar: 2019 Nov to 2019 Dec
|  | 1 |  |  | Appropriate onsite pig waste management piloted | [18 empty] | 0 | 0 | [6 empty] | 0
|  |  | 1 |  | Assessment of current Pig Waste impacts and management practices. |  | 1 | reports | 2000 |  | 1000 | 1000 | [11 empty] | 2000 | 2000 |  | 2000 |  |  |  |  | 2000 | [36 empty] | Project Manager | LC (DLT), ALD, HE, Health Statistic, NEPO (statistic)
|  |  |  | 1 | identify volunteer households to participate in new design and operations |  | 1 | Assessment report | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  | 2 |  | Review alternative pig waste management options, include cost considerations (Dry litter and septic) |  | 1 | Options report | [15 empty] | 0 | 0 | [6 empty] | 0 | [36 empty] | Project Manager | LC (DLT), ALD, HE, MISE | bar: 2020 Jan
|  |  | 3 |  | Commission a consultnat that will design and construct the Dry Litter Piggeries |  | 1 | design layout & construction |  |  | 3000 | [11 empty] | 1000 | 4000 | 4000 |  | 4000 |  |  |  |  | 4000 | [36 empty] | Project Manager | All PSC members | bar: 2020 Jan to 2020 Feb
|  |  |  | 1 | Draft ToR for the consultant |  |  | TOR | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 2 | Selection and contracting of the consultant |  |  | Contract (advertisement etc.) | 2000 |  |  | 2000 | [11 empty] | 2000 | 0 | [6 empty] | 0
|  |  |  | 3 | Actual construction of DLT piggeries by consultant |  | 30 | Completed piggeries and final reports |  |  |  | 100 | [7 empty] | 100 |  | 100 |  | 300 | 9000 |  | 9000 |  |  |  |  | 9000
|  |  | 4 |  | Organise and facilitate stakeholder consultations for appropriate piggery designs |  | 1 | report | 2000 |  |  | 1000 | [10 empty] | 1000 | 2000 | 2000 |  | 2000 |  |  |  |  | 2000 | [36 empty] | LC (DLT) | PM, ALD, HE, MISE, Mayors of piloted areas | bar: 2020 Mar to 2020 Apr
|  |  |  | 1 | Consult with pilot site community and Waste Network on improved design options |  |  | consultation and options report | 0 | [14 empty] | 0 | 0 | [6 empty] | 0
|  |  | 5 |  | Procure materials (requires 3 quotes where possible) |  | 1 | 3 quotes and materials | 8500 | [7 empty] | 7000 |  |  |  |  | 1500 |  | 8500 | 8500 |  | 8500 |  |  |  |  | 8500 | [36 empty] | Project Manager | LC (DLT), MISE, NEPO | bar: 2020 Mar to 2020 May
|  |  | 6 |  | Document the construction process for educaitonal materials linked with 3.1 (video and photo - RPCU Comms to assist) |  | 3 | videos and photos | [7 empty] | 1000 | [7 empty] | 1000 | 3000 |  | 1000 |  | 2000 |  |  | 3000 | [36 empty] | Project Manager | LC (Outreach officer) | bar: 2020 Jun to 2020 Dec
| 2 |  |  |  | Environmental and public health safeguarded via targeted reductions in nutrient and pathogen contamination of coastal areas | [18 empty] | 0 | 0 | [6 empty] | 0
|  | 1 |  |  | Baseline Review conducted | [18 empty] | 0 | 0 | [6 empty] | 0 | bar: 2019 Nov to 2020 Feb
|  |  | 1 |  | Conduct literature review on social/cultural data; governance structure; pig waste management and pollution issues in Kiribati generally and pilot site specifically |  | 1 | baseline data, report, literature review paper | 900 |  |  | 500 |  | 200 | [7 empty] | 200 |  | 900 | 900 | 100 | 700 |  | 100 |  |  | 900 | [36 empty] | Project Manager
|  |  | 2 |  | Faciltiate meeting or interviews on local pollution issues and animal waste management |  | 10 | Meeting minutes and interviews | 180 |  |  | 150 | [9 empty] | 30 |  | 180 | 1800 | 300 | 1500 |  |  |  |  | 1800 | [36 empty] | Project Manager | HE, EH, Health Statistic
|  |  | 3 |  | With baseline WQ data from 2.3 prepare a draft comparison study and site report - including estimation of potential reduced nutrient release |  | 1 | Draft report on pilot site and WQ status | [15 empty] | 0 | 0 | [6 empty] | 0 | [36 empty] | Project Manager | Health Statistic, EH, RPCU
|  |  | 4 |  | Submit draft to ECD and stakeholders for validation |  | 1 | Stakeholder feedback | [15 empty] | 0 | 0 | [6 empty] | 0 | [36 empty] | Project Manager | All PSC members
|  |  | 5 |  | Incorporate feedback and submit final report to technical and steering committee for endorsement |  | 1 | Final report on Pilot Site and WQ | [15 empty] | 0 | 0 | [6 empty] | 0 | [36 empty] | Project Manager | All PSC members
|  |  | 6 |  | Package and publish final evaluation report (RPCU comms to support) |  | 1 | Publshed report | 2500 |  |  | 500 |  | 2000 | [9 empty] | 2500 | 2500 |  | 1000 |  | 1500 |  |  | 2500 | [36 empty] | Project Manager | RPCU
|  | 2 |  |  | Final year evalaution report prepared and endorsed | [18 empty] | 0 | 0 | [6 empty] | 0 | bar: 2019 Dec to 2020 Dec
|  |  | 1 |  | conduct meeting and interviews as above on pig waste management |  | 3 | Meeting minutes and interviews | 450 |  |  | 250 | [9 empty] | 100 | 100 | 450 | 1350 |  | 1350 |  |  |  |  | 1350 | [36 empty] | Project Manager | LC (DLT), EH, Health Statistic, ALD
|  |  | 2 |  | With accumulated WQ data from 2.3 prepare a draft evaluation report including estimations of reduced nutrient release with operational DLT systems |  | 1 | Draft report on pilot site and WQ status | [15 empty] | 0 | 0 | [6 empty] | 0 | [36 empty] | Project Manager | LC (DLT), EH, Health Statistic, ALD
|  |  | 3 |  | Submit draft to ECD and stakeholders for validation |  | 2 | Stakeholder feedback | 500 |  |  | 500 | [11 empty] | 500 | 1000 |  | 1000 |  |  |  |  | 1000 | [36 empty] | Project Manager | All PCS members
|  |  | 4 |  | Incorporate feedback and submit final report to technical and steering committee for endorsement |  | 1 | Final report on Pilot Site and WQ | [15 empty] | 0 | 0 | [6 empty] | 0 | [36 empty] | Project Manager | All PCS members
|  |  | 5 |  | Package and publish final evaluation report (RPCU comms to support) |  | 1 | Publshed report | 2500 |  |  |  |  | 2500 | [9 empty] | 2500 | 2500 | 500 | 500 |  | 1500 |  |  | 2500 | [36 empty] | Project Manager | RPCU
| 3 |  |  |  | National capacity for environmental assessment and water quality analysis increased | [18 empty] | 0 | 0 | [6 empty] | 0
|  | 1 |  |  | Environmental monitoring plan developed | [18 empty] | 0 | 0 | [6 empty] | 0 | bar: 2019 Dec to 2020 Feb
|  |  | 1 |  | Review current and successful env monitoring plans in Kiribati |  | 1 | Review paper | 1000 |  |  |  |  | 1000 | [9 empty] | 1000 | 1000 |  |  |  | 1000 |  |  | 1000 | [36 empty] | Project Manager | RPCU
|  |  | 2 |  | Prepare environmental monitoring plan |  | 1 | plan | 2000 |  |  | 1000 |  | 1000 | [9 empty] | 2000 | 2000 | 500 | 1000 |  | 500 |  |  | 2000 | [36 empty] | Project Manager | RPCU, MISE, EH, ALD, LMD,
|  |  |  | a | develop a monitoring plan including site selection criteria (RPCU to support) |  |  | community monitoring plan | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | b | Workshop the draft plan with Waste Network and identify partners |  |  | consultation reports | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | c | Incorporate consultation outcomes into Monitoring Plan |  |  | monitoring reports and recommendations | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  | 3 |  | WQ training workshop prepared and conducted |  | 1 | report | 3500 |  |  |  |  | 1000 | [8 empty] | 2500 | 3500 | 3500 | 500 | 500 |  | 2500 |  |  | 3500 | [36 empty] | RPCU | Project Manager | bar: 2019 Nov to 2019 Dec
|  |  |  | a | Prepare and conduct WQ training for relevant partners and personnel (RPCU to facilitate) |  |  | training workshop report and materials | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  | 4 |  | Assessment of baseline water quality |  | 1 | report | 2800 |  |  | 500 |  | 2000 | [5 empty] | 300 |  |  |  | 2800 | 2800 | 300 | 2000 |  | 500 |  |  | 2800 | [36 empty] | RPCU | EH, MISE, ALD | bar: 2020 Jan to 2020 Dec
|  |  |  | a | Collect baseline data with stakeholder participation |  |  | raw data and activity reports | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | b | Analyse and report results - incorporate into report above |  |  | baseline WQ report | [15 empty] | 0 | 0 | [6 empty] | 0
|  | 2 |  |  | Implement Env Monitoring Plan | [18 empty] | 0 | 0 | [6 empty] | 0 | bar: 2019 Dec to 2020 Jan
|  |  | 1 |  | Conduct monitoring as per the Env Monitoring Plan - evaluate and adapt as necessary |  |  | activity reports and monitoring reports | [15 empty] | 0 | 0 | [6 empty] | 0 | [36 empty] | Project Manager | EH, MISE (water techninian), ALD
|  |  | 2 |  | Prepare outreach material from assessment reports and deliver through outreach program in 3.1 |  |  | media - newsletter; | [15 empty] | 0 | 0 | [6 empty] | 0 | [36 empty] | Project Manager | LC (Outreach Officer)
3 |  |  |  |  | Information management and community awareness increased in support of sustainable animal waste management and national Integrated Coastal Management | 0 |  |  | 0 | [14 empty] | 0 | 0 | [6 empty] | 0
| 1 |  |  |  | Enhanced access to effective information relating to on-site waste management issues and linkages with environmental and public health to increase public awareness | [18 empty] | 0 | 0 | [6 empty] | 0
|  | 1 |  |  | IW R2R Community Outreach Program developed (guideline from 1.2 and 3.2 - delivered in 1.2 and 1.3) | [18 empty] | 0 | 0 | [6 empty] | 0 | bar: 2019 Oct to 2020 Jan
|  |  | 1 |  | Commission a consultant that will prepare an overarching comprehensive Community Outreach Program (linked with 1.1,1.3 and 3.1) |  | 1 | consultant | 7500 |  | 3500 |  |  | 3000 | [5 empty] | 1000 |  |  |  | 7500 | 7500 | 1000 | 3500 |  | 3000 |  |  | 7500 | [36 empty] | Project Manager | RPCU | DoE & Senior Officials, RPCU
|  |  |  | 1 | Draft ToR for the consultant |  | 1 | TOR | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 2 | Selection and contracting of the consultant |  | 1 | signed contract | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 3 | Actual development of the Community Outreach Program by the consultant |  | 3 | consultations and activity reports final program with M&E plan | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  | 2 |  | Organize/facilitate consultation meetings with relevant stakeholders to obtain best locally appropriate practice on outreach methods, roles of stakeholders etc.. |  | 4 | consultation reports and list of participants | 250 | [13 empty] | 250 | 250 | 1000 |  | 1000 |  |  |  |  | 1000 | [36 empty] | LC (Awareness Raising) | PM, EH, ECD (Outreach Unit), ALD
|  |  | 3 |  | Consultant prepares assessment report specifying the recommendations and requirements for the Community Outreach Strategy including a Monitoring & Evaluation Plan and Budget |  |  | assessment report | [15 empty] | 0 | 0 | [6 empty] | 0 | [36 empty] | LC (Awareness Raising) | Project Manager
|  |  | 4 |  | Present draft Community Outreach Program to ECD and the relevant stakeholders for validation |  | 1 | stakeholder feedback | 500 |  |  | 500 | [11 empty] | 500 | 500 |  | 500 |  |  |  |  | 500 | [36 empty] | LC (Awareness Raising) | ECD, All PSC members
|  |  | 5 |  | Incorporate (where appropriate) inputs from the stakeholders into the Community Outreach Program |  |  | draft Community Outreach Program | [15 empty] | 0 | 0 | [6 empty] | 0 | [36 empty] | LC (Awareness Raising) | Project Manager
|  |  | 6 |  | Finalize and package the community Outreach Program including costings and Monitoring & Evaluation plan |  | 1 | Published Outreach Program | 1000 |  |  | 1000 | [11 empty] | 1000 | 1000 |  | 1000 |  |  |  |  | 1000 | [36 empty] | LC (Awareness Raising) | All, PSC members
|  | 2 |  |  | Training manuals; printed materials and videos developed as per the Outreach Program |  |  | videos; manuals; printed materials | [15 empty] | 0 | 0 | [6 empty] | 0 | bar: 2019 Dec to 2020 Jan
|  |  | 1 |  | Commission a consultant that will prepare additional materials identified in the Outreach Program (e.g video and printed material) |  | 1 | materials | 2000 |  | 2000 | [12 empty] | 2000 | 2000 |  | 2000 |  |  |  |  | 2000 | [36 empty] | Project Manager | RPCU,
|  |  |  | a | Draft ToR for the consultant |  | 1 | TOR | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | b | Selection and contracting of the consultant |  | 1 | signed contract | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | c | Actual prepartion of material by the consultant |  | 1 | materials | [15 empty] | 0 | 0 | [6 empty] | 0
|  | 3 |  |  | IW R2R Community Outreach Program implemented (linked with 1.1 and 2.3) | [18 empty] | 0 | 0 | [6 empty] | 0 | bar: 2020 Jan to 2020 Dec
|  |  | 1 |  | Implement recommended measures indicated in the Community Outreach Program |  | 1 | outreach | 10000 |  |  | 5000 | [10 empty] | 5000 | 10000 | 10000 |  | 10000 |  |  |  |  | 10000 | [36 empty] | LC (Awareness Raising) | ECD (Outreach Unit), EH | DoE & Senior Officials, RPCU
|  |  |  | 1 | Awareness campaign to inform the public on the causes and impacts of animal waste and health (link 3.3) |  |  | implementation reports | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 2 | Construction and maintenance training of Dry Litter Piggeries (link 1.1 and 2.3) |  |  | implementation reports | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 3 | Operational and financing training (link 1.3) |  |  | implementation reports | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  | 4 |  | Monitor the effectiveness of the Outreach Program as per the M&E plan |  |  | participatory interviews and activity reports | [15 empty] | 0 | 0 | [6 empty] | 0 | [36 empty] | project Manager | RPCU | DoE & Senior Officials, RPCU
| 2 |  |  |  | Effective management tools developed to support sustainable uptake of piggery waste management technique | [18 empty] | 0 | 0 | [6 empty] | 0
|  | 1 |  |  | Operational guidelines prepared | [18 empty] | 0 | 0 | [6 empty] | 0 | bar: 2019 Nov to 2020 Mar
|  |  | 1 |  | Conduct background research and collate existing literature on sustainable pig waste management operations |  | 1 |  | 500 |  |  | 500 | [11 empty] | 500 | 500 |  | 500 |  |  |  |  | 500 | [36 empty] | Project Manager | ALD, EH, Health Statistic, LC (DLT), MISE, Volunteer representatives
|  |  |  | 1 | Convene roundtable with relevant partners and ministries to discuss existing guidelines; manuals; procedures |  |  | meeting agendas and minutes | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 2 | Convene stakeholder consultations to discuss best methods for presenting operational materials (format; language etc.) |  |  | consultation minutes and outcomes paper | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 3 | Prepare paper highlighting preferred method of receiving information and gaps in available management tools |  |  | Gap analysis report with options for final product | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 4 | Present analsyis report to TAC and community for comment |  |  | Comment or approved report | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  | 2 |  | Prepare operational guideline for (DLT?) and compost management |  | 1 |  | 500 |  |  | 500 | [11 empty] | 500 | 500 |  | 500 |  |  |  |  | 500 | [36 empty] | LC (DLT) | ALD, EH, KOFA, MISE, Volunteer representatives
|  |  |  | 1 | With support as necessary from partner/agencies prepare draft text for operational guideline (piggery system and compost may be together or seperated) |  |  | draft text for guidelines | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 2 | Present to TAC and community for feedback |  |  | Feedback review | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 3 | Incorporate feedback and submit final Guidelines to technical and steering committee for endorsement |  |  | final endorsed guidelines | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 4 | Package and publish guidelines (RPCU comms to support) |  |  | published final guidelines | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  | 3 |  | Deliver guideline and training through the Waste Network and Outreach Program (linked with 1.1 and 3.1) | [18 empty] | 0 | 0 | [6 empty] | 0 | [36 empty] | LC (DLT), LC (Outreach Officer) | ALD, MISE, RPCU, Volunteer representatives | bar: 2020 Jan to 2020 Feb
|  |  |  | 1 | evaluate effectiveness of guidelines and update as required. |  |  | evaluation reports | [15 empty] | 0 | 0 | [6 empty] | 0
| 3 |  |  |  | Improved knowledge base and access for effective decision making | [18 empty] | 0 | 0 | [6 empty] | 0
|  | 1 |  |  | Database/knowledge mamagement system established | [18 empty] | 0 | 0 | [6 empty] | 0 | bar: 2020 Jan to 2020 Feb
|  |  | 1 |  | Review exisitng project and national databases and identify opportunities and gaps for establishing Waste Management Network database |  | 1 | Review report | [15 empty] | 0 | 0 | [6 empty] | 0 | [36 empty] | LC (D.Base) | ECD (IT personnel), RPCU | DoE & Senior Officials, RPCU
|  |  | 2 |  | Commission a consultant that will develop a local server or online database that can link to/embed withing exisitng website/s |  | 1 | consultant - dbase | 2000 |  | 2000 | [12 empty] | 2000 | 2000 |  | 2000 |  |  |  |  | 2000 | [36 empty] | Project Manager | ECD (IT personnel), RPCU | DoE & Senior Officials, RPCU
|  |  |  | a | Draft ToR for the consultant |  |  | TOR | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | b | Selection and contracting of the consultant |  |  | signed contract | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | c | Actual development of database by the consultant |  |  | Activity reports; consultations; final database and schema | [15 empty] | 0 | 0 | [6 empty] | 0
|  | 2 |  |  | Database/knowledge mamagement system populated | [18 empty] | 0 | 0 | [6 empty] | 0 | bar: 2019 Nov to 2020 Jun
|  |  | 1 |  | Collate all existing and historical data and information relating to animal and human waste management in Kiribati and Tarawa specifically. Including project; academic; national data on WQ and animal health |  | 1 | repository of info/data | 500 |  |  | 500 | [11 empty] | 500 | 500 |  | 500 |  |  |  |  | 500 | [36 empty] | Project Manager | EH, Health Statistic, ALD, MISE (water unit)
|  |  | 2 |  | Prepare (in association with other community consultations) report and data for Traditional Ecological Knowledge (TEK) |  | 1 | report | 4000 |  |  | 3000 | [9 empty] | 1000 |  | 4000 | 4000 | 500 | 3000 |  | 500 |  |  | 4000 | [36 empty] | Project Manager | RPCU, ALD, MISE, ECD (Outreach Unit)
|  |  |  | 1 | Review exisiting TEK techniques and questionaires |  |  | review paper | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 2 | Develop a locally appropriate TEK questionaire |  |  | TEK questionnaire | [15 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 3 | Conduct interviews with relevant stakeholders |  | 3 | participatory interviews and activity reports | 100 |  |  | 100 | [11 empty] | 100 | 300 |  | 300 |  |  |  |  | 300
|  |  |  | 4 | Prepare final TEK reports and submit to ECD and stakeholders for validation |  | 1 | Final TEK report | 1200 |  |  | 200 |  | 1000 | [9 empty] | 1200 | 1200 |  | 1000 |  | 200 |  |  | 1200
|  |  | 3 |  | Prepare all relevant IW R2R and STAR Project data for upload |  |  | clean prepared data | [15 empty] | 0 | 0 | [6 empty] | 0 | [36 empty] | LC (D.Base) | Project Manager | bar: 2020 Feb to 2020 Dec
|  |  | 4 |  | Upload all relevant data and monitor access |  |  | populated database | [15 empty] | 0 | 0 | [6 empty] | 0 | [36 empty] | LC (D.Base) | Project Manager | bar: 2020 Feb to 2020 Dec
|  |  | 5 |  | Submit monitoring reports to ECD and PSC for feedback |  |  | monitoring reports | [15 empty] | 0 | 0 | [6 empty] | 0 | [36 empty] | LC (D.Base) | Project Manager | bar: 2020 Nov to 2020 Dec
| 4 |  |  |  | Diagnostic & state of coast report | 2 | 1 | report | 2000 |  |  | 2000 | [11 empty] | 2000 | 2000 |  |  |  | 2000 |  |  | 2000 | [36 empty] | RPCU | Project Manager | bar: 2021 Jan to 2021 Jun
|  |  |  | 1 | Collection and provision of data and information to the Consultant | 2 |  |  | 0 | [14 empty] | 0 | 0 | [6 empty] | 0 | bar: 2021 Jan to 2021 Jun
|  |  |  | 2 | Assist to coordinate stakeholder consultation | 2 |  |  | 0 | [14 empty] | 0 | 0 | [6 empty] | 0 | bar: 2021 Jan to 2021 Jun
|  |  |  | 3 | Submit to PSC and Cabinet for approval | 2 | [17 empty] | 0 | 0 | [6 empty] | 0 | bar: 2021 Jan to 2021 Jun
|  |  |  | 4 | Assist to prepare and finalize the diagnostic report | 2 | [17 empty] | 0 | 0 | [6 empty] | 0 | bar: 2021 Jan to 2021 Jun
| 5 |  |  |  | National R2R Strategic Action Plan | 2 | 1 | report | 2000 |  |  | 2000 | [11 empty] | 2000 | 2000 |  |  |  | 2000 |  |  | 2000 | [36 empty] | Project Manager | RPCU | bar: 2021 Jan to 2021 Jun
|  |  |  | 1 | assist, prepare and draft national strategic action plan | 2 |  |  | 0 | [14 empty] | 0 | 0 | [6 empty] | 0 | bar: 2021 Jan to 2021 Jun
|  |  |  | 2 | Submit to PSC and Cabinet for approval | 2 | [17 empty] | 0 | 0 | [6 empty] | 0 | bar: 2021 Jan to 2021 Jun
|  |  |  | 3 | finalize, print and publish the final action plan | 2 |  |  | 0 | [14 empty] | 0 | 0 | [6 empty] | 0 | bar: 2021 Jan to 2021 Jun
|  |  |  | 4 | monitor the implementation and impacts of recommendations | 2 | [17 empty] | 0 | 0 | [6 empty] | 0 | bar: 2021 Jan to 2021 Jun
[5 empty] | Sub-Total |  |  |  |  | 0 | 21500 | 39200 | 0 | 14000 | 0 | 1000 | 9000 | 0 | 1500 | 1400 | 0 | 2930 | 15450 | 105980 | 132550 | 10150 | 96650 | 0 | 25750 | 0 | 0 | 132550
Summary Sub-activities |  |  |  |  | not yet started | 12 | 60%
[5 empty] | ongoing | 0 | 0%
[5 empty] | completed | 8 | 40%
[5 empty] | Total | 20 | 100%
Summary Major activities |  |  |  |  | not yet started | 0 | #DIV/0!
[5 empty] | ongoing | 0 | #DIV/0!
[5 empty] | completed | 0 | #DIV/0!
[5 empty] | Total | 0 | #DIV/0!
Summary Outputs |  |  |  |  | not yet started | 0 | #DIV/0!
[5 empty] | ongoing | 0 | #DIV/0!
[5 empty] | completed | 0 | #DIV/0!
[5 empty] | Total | 0 | #DIV/0!
Summary Outcomes |  |  |  |  | not yet started | 2 | 50%
[5 empty] | ongoing | 0 | 0%
[5 empty] | completed | 2 | 50%
[5 empty] | Total | 4 | 100%
Summary Components |  |  |  |  | not yet started | 3 | 100%
[5 empty] | ongoing | 0 | 0%
[5 empty] | completed | 0 | 0%
[5 empty] | Total | 3 | 100%
0
1
2

## Fiji (hidden)
Detailed Work and Financial Plan
Project Title: Implementing Ridge to Reef approach to preserve ecosystems services, sequester carbon, improve climate resilience and sustain livelihoods in Fiji
Implementing Partner: Ministry of Local Government, Housing and Environment
Implementation Period: March 2018 to March 2021 (4 years)
Version (Indicate the Date): March 13, 2018
Outcome |  |  |  | Output/ Major activity/ Sub activity | Status | Quantity | Unit of Measure | Unit price | Detailed components of the unit price | [6 empty] | Cost per output & activity | Fund Sources |  |  |  |  | Implementation Period | [47 empty] | Responsible Parties |  |  | REMARKS
| Outputs | Major Activity | Sub-Activity | [5 empty] | Personnel/ Consultant/s (Person x Daily Rate x Days) | Estimated Travel & Accomm Cost | Workshop venue | Food | Procurement or rental of Equipments, materials, publication, etc. | Others | Subtotal Cost per unit |  | National Government counterpart | STAR Project | Others 1 | Others 2 | Total Budget (in USD) | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021
[22 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Main/Lead | Support | Others
0 |  |  |  | Fij Project effectively managed. | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  |  | Personnel Cost | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 |  | Project Manager (Remuneration - Salary+Benefits) | 0 | 48 | Monthly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 |  | Finance Assistant (time allocation) | 0 | 48 | Monthly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 |  |  | 0
4
5
6
|  | 7 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 |  |  | Project operations | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 |  | Other Operational costs (office supplies, etc.) | 0 | 48 | Monthly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 |  | Office space | 0 | 48 | Monthly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 2018 Nov: 0; 2018 Dec: 0; 2019 Jan: 0; 2019 Feb: 0; 2019 Mar: 0; 2019 Apr: 0; 2019 May: 0; 2019 Jun: 0; 2019 Jul: 0; 2019 Aug: 0; 2019 Sept: 0; 2019 Oct: 0; 2019 Nov: 0; 2019 Dec: 0; 2021 Jan: 0; 2021 Feb: 0; 2021 Mar: 0; 2021 Apr: 0; 2021 May: 0; 2021 Jun: 0; 2021 Jul: 0; 2021 Aug: 0; 2021 Sept: 0; 2021 Oct: 0; 2021 Nov: 0; 2021 Dec: 0
|  | 3 |  | Utilities (water, electricity, communications) | 0 | 48 | Monthly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 |  | Attendance to Semi-Annual National Project Steering Committee Meetings | 0 | 8 | Meeting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5 | [5 empty] | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 6 | [5 empty] | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 2018 Nov: 0; 2018 Dec: 0; 2019 Jan: 0; 2019 Feb: 0; 2019 Mar: 0; 2019 Apr: 0; 2019 May: 0; 2019 Jun: 0; 2019 Jul: 0; 2019 Aug: 0; 2019 Sept: 0; 2019 Oct: 0; 2019 Nov: 0; 2019 Dec: 0; 2021 Jan: 0; 2021 Feb: 0; 2021 Mar: 0; 2021 Apr: 0; 2021 May: 0; 2021 Jun: 0; 2021 Jul: 0; 2021 Aug: 0; 2021 Sept: 0; 2021 Oct: 0; 2021 Nov: 0; 2021 Dec: 0
|  | 7 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 |  |  |  | Improved management effectiveness of existing and new protected areas | 0 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  |  | Expanded terrestrial and marine PA system: Three new terrestrial protected areas (Tunuloa, Tuva and Vunivia) delineated and formally established to conserve biodiversity, especially unprotected ecosystems and threatened species, and maintain ecosystem goods and services in an R2R context. One new MPA (Tuva) develop and incorporated into FLMMA. | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2018 Nov: 0; 2018 Dec: 0; 2019 Jan: 0; 2019 Feb: 0; 2019 Mar: 0; 2019 Apr: 0; 2019 May: 0; 2019 Jun: 0; 2019 Jul: 0; 2019 Aug: 0; 2019 Sept: 0; 2019 Oct: 0; 2019 Nov: 0; 2019 Dec: 0; 2021 Jan: 0; 2021 Feb: 0; 2021 Mar: 0; 2021 Apr: 0; 2021 May: 0; 2021 Jun: 0; 2021 Jul: 0; 2021 Aug: 0; 2021 Sept: 0; 2021 Oct: 0; 2021 Nov: 0; 2021 Dec: 0
1
2
3
4
|  | 2 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
2
3
4
|  | 3 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 | 2018 Aug: 0; 2018 Nov: 0; 2018 Dec: 0; 2019 Jan: 0; 2019 Feb: 0; 2019 Mar: 0; 2019 Apr: 0; 2019 May: 0; 2019 Jun: 0; 2019 Jul: 0; 2019 Aug: 0; 2019 Sept: 0; 2019 Oct: 0; 2019 Nov: 0; 2019 Dec: 0; 2021 Jan: 0; 2021 Feb: 0; 2021 Mar: 0; 2021 Apr: 0; 2021 May: 0; 2021 Jun: 0; 2021 Jul: 0; 2021 Aug: 0; 2021 Sept: 0; 2021 Oct: 0; 2021 Nov: 0; 2021 Dec: 0
1
2
3
4
4
1
2
3
4
5
1
2
3
4
6
1
2
3
4
7
1
2
3
4
| 2 |  |  | Improved Management of PA System: One existing terrestrial protected area (Sovi Basin) and six existing LMMAs/MPAs strengthened through development and/or implementation of management plans following the Community Conserved Areas (CCA)/LMMA approach to conserve biodiversity and maintain ecosystem goods and services in a R2R context. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
2 |  |  |  | Improved financial sustainability for terrestrial and marine protected area systems
| 1 |  |  | Valuation of biodiversity and other ecosystem services completed in at least two sites as basis for sustainable conservation finance approaches. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2018 Sept: 0; 2018 Nov: 0; 2018 Dec: 0; 2019 Jan: 0; 2019 Feb: 0; 2019 Mar: 0; 2019 Apr: 0; 2019 May: 0; 2019 Jun: 0; 2019 Jul: 0; 2019 Aug: 0; 2019 Sept: 0; 2019 Oct: 0; 2019 Nov: 0; 2019 Dec: 0; 2021 Jan: 0; 2021 Feb: 0; 2021 Mar: 0; 2021 Apr: 0; 2021 May: 0; 2021 Jun: 0; 2021 Jul: 0; 2021 Aug: 0; 2021 Sept: 0; 2021 Oct: 0; 2021 Nov: 0; 2021 Dec: 0
|  | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2018 Nov: 0; 2018 Dec: 0; 2019 Jan: 0; 2019 Feb: 0; 2019 Mar: 0; 2019 Apr: 0; 2019 May: 0; 2019 Jun: 0; 2019 Jul: 0; 2019 Aug: 0; 2019 Sept: 0; 2019 Oct: 0; 2019 Nov: 0; 2019 Dec: 0; 2021 Jan: 0; 2021 Feb: 0; 2021 Mar: 0; 2021 Apr: 0; 2021 May: 0; 2021 Jun: 0; 2021 Jul: 0; 2021 Aug: 0; 2021 Sept: 0; 2021 Oct: 0; 2021 Nov: 0; 2021 Dec: 0
|  | 2 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2018 Nov: 0; 2018 Dec: 0; 2019 Jan: 0; 2019 Feb: 0; 2019 Mar: 0; 2019 Apr: 0; 2019 May: 0; 2019 Jun: 0; 2019 Jul: 0; 2019 Aug: 0; 2019 Sept: 0; 2019 Oct: 0; 2019 Nov: 0; 2019 Dec: 0; 2021 Jan: 0; 2021 Feb: 0; 2021 Mar: 0; 2021 Apr: 0; 2021 May: 0; 2021 Jun: 0; 2021 Jul: 0; 2021 Aug: 0; 2021 Sept: 0; 2021 Oct: 0; 2021 Nov: 0; 2021 Dec: 0
4
5
6
7
| 2 |  |  | Review of user fee system and options for LMMA in Fiji, including development and implementation of user fee system for Tuva/Natadola. | 0 |  |  | 0 | [6 empty] | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 6 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 |  |  | Assessment completed on the existing Trust Fund for Sovi basin and potential for its utilization by planned new R2R PAs; guidelines for fund management and utilization reviewed and recommendations formulated. | 0 |  |  | 0 | [6 empty] | 0 | #REF! |  |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 |  |  | 0 |  |  | 0 | [6 empty] | 0 | #REF! |  |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 |  |  | 0
|  | 5 |  |  | 0
|  | 6 |  |  | 0
3 |  |  |  | Carbon stocks restored and enhanced in priority catchments | 0 |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  |  | Restoration and enhancement of carbon stocks in degraded forests in six priority water catchments using native tree species commencing with demonstration/research plots in each catchment. | 0 |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 6 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 7 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 |  |  | National sectoral policies strengthened with INRM (covering land, water, forests, biodiversity) in the following sectors: forestry, agriculture, lands, fisheries, iTaukei, tourism, and health. | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 |  |  | 0 |  |  | 0 | [6 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 |  |  | 0 |  |  | 0 | [6 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 |  |  | National and Provincial government - relevant agency staff including RokoTuis, Assistant Rokos and Conservation Officers, trained for INRM through leadership and/or participation in project activities. | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 6 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 7 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 |  |  | Empowered communities as a result of participation in: 1) formulation of PA management plans and catchment management plans; 2) alignment of community livelihoods with local priorities; 3) development of market-based instruments within the project, including ecosystem services. | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 6 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  |  |  | Improved data and information systems on biodiversity; land, forests, coastal and marine management; climate change and best practices | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  |  | Information portal established for easily accessible data and information on project outcomes based on biodiversity, forests, coasts, land and water management practices, including climate change. | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 |  |  | A knowledge management component is integrated into the ToR of all project staff to streamline information management process. | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 |  |  | A portal policy developed to guide the structure of the data and information received. | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 |  |  | 0 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 |  |  | 0 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 |  |  | 0
|  | 4 |  |  | 0
|  | 5 |  |  | 0
| 4 |  |  | A knowledge management officer is recruited to ensure that the data and information captured from project activities are catalogued, archived and maintained in a meaningful way. | 0
|  | 1 |  |  | 0
|  | 2 |  |  | 0
|  | 3 |  |  | 0
|  | 4 |  |  | 0
|  | 5 |  |  | 0
| 5 |  |  | Discoverability and accessibility of the projects information portal is ascertained and addressed. | 0
|  | 1 |  |  | 0
|  | 2 |  |  | 0
|  | 3 |  |  | 0
|  | 4 |  |  | 0
|  | 5 |  |  | 0
| 6 |  |  | Facilitate linkages with other relevant information portals in the region such as the Pacific Climate Change Portal, Disaster Net, University of the South Pacific Research Portal and the USP-EU GCCA knowledge center. | 0
|  | 1 |  |  | 0
|  | 2 |  |  | 0
|  | 3 |  |  | 0
|  | 4 |  |  | 0
|  | 5 |  |  | 0
| 7 |  |  | A communications strategy of the project Portal is designed and implemented so relevant partners are aware and can access information of the project from the portal. | 0
1
2
3
4
5
| 8 |  |  | Knowledge products (brochures, flyers, videos) on all thematic/focal areas and best practices developed and disseminated through various print and broadcast media.
1
2
3
4
5
| 9 |  |  | Exchange visits by community leaders, resource owners and farmers to observe catchment use and management (including best, good and bad practices).
1
2
3
4
5
National Project Management |  |  |  | State of the Cost Report available |  | 1 | SCR Report | 7005 | 3800 | 1100 | 1000 | 1000 | 105 | 0 | 7005 | 7250 | 0 | 0 |  | 0 | 0 | bar: 2018 Jun
|  | 1 |  | Conduct of biodiversity assessment survey |  | 1 | SCR Report | 4350 | 2400 | 900 | 500 | 500 | 50 | 0 | 4350 | 4350 | 0 | 0 |  | 0 | 0 | bar: 2018 Jan to 2018 Apr
|  |  | 1 | Conduct data collection and occular inspection |  | 1 | District or area | 2100 | 1400 | 700 | 0 | 0 | 0 | 0 | 2100 | 2100 |  |  |  |  | 0 | bar: 2018 Jan to 2018 Mar
|  |  | 2 | Conduct consultation meetings |  | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  |  | 0 | bar: 2018 Feb to 2018 Mar
|  |  | 3 | Perform data consolidation, analysis and interpretation |  | 1 | District or area | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 600 |  |  |  |  | 0 | bar: 2018 Apr
|  |  | 4 |  |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0
|  |  | 5 |  |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0
|  | 2 |  | Packgaging of the State of the Cost Report (SCR) |  | 1 | SCR Report | 2655 | 1400 | 200 | 500 | 500 | 55 | 0 | 2655 | 2900 | 0 | 0 |  | 0 | 0 | bar: 2018 Apr to 2018 Jun
|  |  | 1 | Drafting of the SCR |  | 1 | SCR Report | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 700 |  |  |  |  | 0 | bar: 2018 Apr
|  |  | 2 | Conduct validation meetings on the biodiversity assessment results |  | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  |  | 0 | bar: 2018 Apr to 2018 May
|  |  | 3 | Revision/editing, finalization of the SCR |  | 1 | SCR Report | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 300 |  |  |  |  | 0 | bar: 2018 May
|  |  | 4 | Publication of the SCR |  | 50 | copies | 5 | 0 | 0 | 0 | 0 | 5 |  | 5 | 250 |  |  |  |  | 0 | bar: 2018 Jun
|  |  |  | State of the Cost Report available |  | 1 | SCR Report | 7005 | 3800 | 1100 | 1000 | 1000 | 105 | 0 | 7005 | 7250 | 0 | 0 |  | 0 | 0 | bar: 2018 Jun
|  | 1 |  | Conduct of biodiversity assessment survey |  | 1 | SCR Report | 4350 | 2400 | 900 | 500 | 500 | 50 | 0 | 4350 | 4350 | 0 | 0 |  | 0 | 0 | bar: 2018 Jan to 2018 Apr
|  |  | 1 | Conduct data collection and occular inspection |  | 1 | District or area | 2100 | 1400 | 700 | 0 | 0 | 0 | 0 | 2100 | 2100 |  |  |  |  | 0 | bar: 2018 Jan to 2018 Mar
|  |  | 2 | Conduct consultation meetings |  | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  |  | 0 | bar: 2018 Feb to 2018 Mar
|  |  | 3 | Perform data consolidation, analysis and interpretation |  | 1 | District or area | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 600 |  |  |  |  | 0 | bar: 2018 Apr
|  |  | 4 |  |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0
|  |  | 5 |  |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0
|  | 2 |  | Packgaging of the State of the Cost Report (SCR) |  | 1 | SCR Report | 2655 | 1400 | 200 | 500 | 500 | 55 | 0 | 2655 | 2900 | 0 | 0 |  | 0 | 0 | bar: 2018 Apr to 2018 Jun
|  |  | 1 | Drafting of the SCR |  | 1 | SCR Report | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 700 |  |  |  |  | 0 | bar: 2018 Apr
|  |  | 2 | Conduct validation meetings on the biodiversity assessment results |  | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  |  | 0 | bar: 2018 Apr to 2018 May
|  |  | 3 | Revision/editing, finalization of the SCR |  | 1 | SCR Report | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 300 |  |  |  |  | 0 | bar: 2018 May
|  |  | 4 | Publication of the SCR |  | 50 | copies | 5 | 0 | 0 | 0 | 0 | 5 |  | 5 | 250 |  |  |  |  | 0 | bar: 2018 Jun
|  |  | 2 | Conduct validation meetings on the biodiversity assessment results |  | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  |  | 0 | bar: 2018 Apr to 2018 May
|  |  | 3 | Revision/editing, finalization of the SCR |  | 1 | SCR Report | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 300 |  |  |  |  | 0 | bar: 2018 May
|  |  | 4 | Publication of the SCR |  | 50 | copies | 5 | 0 | 0 | 0 | 0 | 5 |  | 5 | 250 |  |  |  |  | 0 | bar: 2018 Jun
Support from SPC |  |  |  | State of the Cost Report available |  | 1 | SCR Report | 7005 | 3800 | 1100 | 1000 | 1000 | 105 | 0 | 7005 | 7250 | 0 | 0 |  | 0 | 0 | bar: 2018 Jun
|  | 1 |  | Conduct of biodiversity assessment survey |  | 1 | SCR Report | 4350 | 2400 | 900 | 500 | 500 | 50 | 0 | 4350 | 4350 | 0 | 0 |  | 0 | 0 | bar: 2018 Jan to 2018 Apr
|  |  | 1 | Conduct data collection and occular inspection |  | 1 | District or area | 2100 | 1400 | 700 | 0 | 0 | 0 | 0 | 2100 | 2100 |  |  |  |  | 0 | bar: 2018 Jan to 2018 Mar
|  |  | 2 | Conduct consultation meetings |  | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  |  | 0 | bar: 2018 Feb to 2018 Mar
|  |  | 3 | Perform data consolidation, analysis and interpretation |  | 1 | District or area | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 600 |  |  |  |  | 0 | bar: 2018 Apr
|  |  | 4 |  |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0
|  |  | 5 |  |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0
|  | 2 |  | Packgaging of the State of the Cost Report (SCR) |  | 1 | SCR Report | 2655 | 1400 | 200 | 500 | 500 | 55 | 0 | 2655 | 2900 | 0 | 0 |  | 0 | 0 | bar: 2018 Apr to 2018 Jun
|  |  | 1 | Drafting of the SCR |  | 1 | SCR Report | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 700 |  |  |  |  | 0 | bar: 2018 Apr
|  |  | 2 | Conduct validation meetings on the biodiversity assessment results |  | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  |  | 0 | bar: 2018 Apr to 2018 May
|  |  | 3 | Revision/editing, finalization of the SCR |  | 1 | SCR Report | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 300 |  |  |  |  | 0 | bar: 2018 May
|  |  | 4 | Publication of the SCR |  | 50 | copies | 5 | 0 | 0 | 0 | 0 | 5 |  | 5 | 250 |  |  |  |  | 0 | bar: 2018 Jun
|  |  |  | Grand Total | [11 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0
1
2