## Original (hidden)
Detailed Work and Financial Plan
Project Title:
Recipient:
Implementation Period:
Version:
Reference No. |  |  | Output/ Major activity/ Sub activity | Quantity | Unit of Measure | Unit price | Detailed components of the unit price | [6 empty] | Cost per output and activity | Fund Sources |  |  |  | Period Coverage | [35 empty] | Responsible Party |  |  | REMARKS
[7 empty] | Personnel/ Consultant/s (Person x Daily Rate x Days) | Estimated Travel & Accomm Cost | Workshop venue | Food | Procurement or rental of Equipments, materials, publication, etc. | Others | Subtotal Cost per unit |  | National Budget | SPC-R2R | Others | Total Budget (in FJD) | 2018 | [11 empty] | 2019 | [11 empty] | 2020
[19 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | Main/Lead | Support | Others
1 |  |  | Appropriate onsite pig waste management piloted | 1 | 0 | 4350 | 2400 | 900 | 500 | 500 | 50 | 0 | 4350 | 4350 | 0 | 0 | 0 | 0 | bar: 2018 J
| 1 |  |  | 1 |  | 4350 | 2400 | 900 | 500 | 500 | 50 | 0 | 4350 | 4350 | 0 | 0 | 0 | 0 | bar: 2018 J to 2018 A
|  | 1 | Assessment of Pig Waste impacts and management practices. | 1 | District or area | 2100 | 1400 | 700 | 0 | 0 | 0 | 0 | 2100 | 2100 |  |  |  | 0 | bar: 2018 J to 2018 M
|  | 2 | Review pig waste management options, include cost considerations | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  | 0 | bar: 2018 F to 2018 M
|  | 3 | Consult, design and construct X number of improved domestic pig pen. (dry litter) | 1 | District or area | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 600 |  |  |  | 0 | bar: 2018 A
|  | 4 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
|  | 5 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
| 2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2018 A to 2018 J
|  | 1 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 |  |  |  | 0 | bar: 2018 A
|  | 2 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 |  |  |  | 0 | bar: 2018 A to 2018 M
|  | 3 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 |  |  |  | 0 | bar: 2018 M
|  | 4 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0 | bar: 2018 J
2 |  |  | State of the Cost Report available | 1 | SCR Report | 7005 | 3800 | 1100 | 1000 | 1000 | 105 | 0 | 7005 | 7250 | 0 | 0 | 0 | 0 | bar: 2018 J
| 1 |  |  | 1 | SCR Report | 4350 | 2400 | 900 | 500 | 500 | 50 | 0 | 4350 | 4350 | 0 | 0 | 0 | 0 | bar: 2018 J to 2018 A
|  | 1 | 1.2.1.1 Assessment of baseline nutrient and pathogen loads from current pig waste management practices | 1 | District or area | 2100 | 1400 | 700 | 0 | 0 | 0 | 0 | 2100 | 2100 |  |  |  | 0 | bar: 2018 J to 2018 M
|  | 2 | 1.2.1.2 Monitoring program inititated with construction of improved domestic pig pen | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  | 0 | bar: 2018 F to 2018 M
|  | 3 | 1.2.1.3 Assessment of reduction in nutrient and pathogen loads from improved domestic pig waste management practices | 1 | District or area | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 600 |  |  |  | 0 | bar: 2018 A
|  | 4 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
|  | 5 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
| 2 |  | Packgaging of the State of the Cost Report (SCR) | 1 | SCR Report | 2655 | 1400 | 200 | 500 | 500 | 55 | 0 | 2655 | 2900 | 0 | 0 | 0 | 0 | bar: 2018 A to 2018 J
|  | 1 | Drafting of the SCR | 1 | SCR Report | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 700 |  |  |  | 0 | bar: 2018 A
|  | 2 | Conduct validation meetings on the biodiversity assessment results | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  | 0 | bar: 2018 A to 2018 M
|  | 3 | Revision/editing, finalization of the SCR | 1 | SCR Report | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 300 |  |  |  | 0 | bar: 2018 M
|  | 4 | Publication of the SCR | 50 | copies | 5 | 0 | 0 | 0 | 0 | 5 |  | 5 | 250 |  |  |  | 0 | bar: 2018 J
3 |  |  | State of the Cost Report available | 1 | SCR Report | 7005 | 3800 | 1100 | 1000 | 1000 | 105 | 0 | 7005 | 7250 | 0 | 0 | 0 | 0 | bar: 2018 J
| 1 |  | Conduct of biodiversity assessment survey | 1 | SCR Report | 4350 | 2400 | 900 | 500 | 500 | 50 | 0 | 4350 | 4350 | 0 | 0 | 0 | 0 | bar: 2018 J to 2018 A
|  | 1 | Conduct data collection and occular inspection | 1 | District or area | 2100 | 1400 | 700 | 0 | 0 | 0 | 0 | 2100 | 2100 |  |  |  | 0 | bar: 2018 J to 2018 M
|  | 2 | Conduct consultation meetings | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  | 0 | bar: 2018 F to 2018 M
|  | 3 | Perform data consolidation, analysis and interpretation | 1 | District or area | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 600 |  |  |  | 0 | bar: 2018 A
|  | 4 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
|  | 5 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
| 2 |  | Packgaging of the State of the Cost Report (SCR) | 1 | SCR Report | 2655 | 1400 | 200 | 500 | 500 | 55 | 0 | 2655 | 2900 | 0 | 0 | 0 | 0 | bar: 2018 A to 2018 J
|  | 1 | Drafting of the SCR | 1 | SCR Report | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 700 |  |  |  | 0 | bar: 2018 A
|  | 2 | Conduct validation meetings on the biodiversity assessment results | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  | 0 | bar: 2018 A to 2018 M
|  | 3 | Revision/editing, finalization of the SCR | 1 | SCR Report | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 300 |  |  |  | 0 | bar: 2018 M
|  | 4 | Publication of the SCR | 50 | copies | 5 | 0 | 0 | 0 | 0 | 5 |  | 5 | 250 |  |  |  | 0 | bar: 2018 J
4 |  |  | State of the Cost Report available | 1 | SCR Report | 7005 | 3800 | 1100 | 1000 | 1000 | 105 | 0 | 7005 | 7250 | 0 | 0 | 0 | 0 | bar: 2018 J
| 1 |  | Conduct of biodiversity assessment survey | 1 | SCR Report | 4350 | 2400 | 900 | 500 | 500 | 50 | 0 | 4350 | 4350 | 0 | 0 | 0 | 0 | bar: 2018 J to 2018 A
|  | 1 | Conduct data collection and occular inspection | 1 | District or area | 2100 | 1400 | 700 | 0 | 0 | 0 | 0 | 2100 | 2100 |  |  |  | 0 | bar: 2018 J to 2018 M
|  | 2 | Conduct consultation meetings | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  | 0 | bar: 2018 F to 2018 M
|  | 3 | Perform data consolidation, analysis and interpretation | 1 | District or area | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 600 |  |  |  | 0 | bar: 2018 A
|  | 4 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
|  | 5 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
| 2 |  | Packgaging of the State of the Cost Report (SCR) | 1 | SCR Report | 2655 | 1400 | 200 | 500 | 500 | 55 | 0 | 2655 | 2900 | 0 | 0 | 0 | 0 | bar: 2018 A to 2018 J
|  | 1 | Drafting of the SCR | 1 | SCR Report | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 700 |  |  |  | 0 | bar: 2018 A
|  | 2 | Conduct validation meetings on the biodiversity assessment results | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  | 0 | bar: 2018 A to 2018 M
|  | 3 | Revision/editing, finalization of the SCR | 1 | SCR Report | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 300 |  |  |  | 0 | bar: 2018 M
|  | 4 | Publication of the SCR | 50 | copies | 5 | 0 | 0 | 0 | 0 | 5 |  | 5 | 250 |  |  |  | 0 | bar: 2018 J
5 |  |  | State of the Cost Report available | 1 | SCR Report | 7005 | 3800 | 1100 | 1000 | 1000 | 105 | 0 | 7005 | 7250 | 0 | 0 | 0 | 0 | bar: 2018 J
| 1 |  | Conduct of biodiversity assessment survey | 1 | SCR Report | 4350 | 2400 | 900 | 500 | 500 | 50 | 0 | 4350 | 4350 | 0 | 0 | 0 | 0 | bar: 2018 J to 2018 A
|  | 1 | Conduct data collection and occular inspection | 1 | District or area | 2100 | 1400 | 700 | 0 | 0 | 0 | 0 | 2100 | 2100 |  |  |  | 0 | bar: 2018 J to 2018 M
|  | 2 | Conduct consultation meetings | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  | 0 | bar: 2018 F to 2018 M
|  | 3 | Perform data consolidation, analysis and interpretation | 1 | District or area | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 600 |  |  |  | 0 | bar: 2018 A
|  | 4 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
|  | 5 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
| 2 |  | Packgaging of the State of the Cost Report (SCR) | 1 | SCR Report | 2655 | 1400 | 200 | 500 | 500 | 55 | 0 | 2655 | 2900 | 0 | 0 | 0 | 0 | bar: 2018 A to 2018 J
|  | 1 | Drafting of the SCR | 1 | SCR Report | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 700 |  |  |  | 0 | bar: 2018 A
|  | 2 | Conduct validation meetings on the biodiversity assessment results | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  | 0 | bar: 2018 A to 2018 M
|  | 3 | Revision/editing, finalization of the SCR | 1 | SCR Report | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 300 |  |  |  | 0 | bar: 2018 M
|  | 4 | Publication of the SCR | 50 | copies | 5 | 0 | 0 | 0 | 0 | 5 |  | 5 | 250 |  |  |  | 0 | bar: 2018 J
6 |  |  | State of the Cost Report available | 1 | SCR Report | 7005 | 3800 | 1100 | 1000 | 1000 | 105 | 0 | 7005 | 7250 | 0 | 0 | 0 | 0 | bar: 2018 J
| 1 |  | Conduct of biodiversity assessment survey | 1 | SCR Report | 4350 | 2400 | 900 | 500 | 500 | 50 | 0 | 4350 | 4350 | 0 | 0 | 0 | 0 | bar: 2018 J to 2018 A
|  | 1 | Conduct data collection and occular inspection | 1 | District or area | 2100 | 1400 | 700 | 0 | 0 | 0 | 0 | 2100 | 2100 |  |  |  | 0 | bar: 2018 J to 2018 M
|  | 2 | Conduct consultation meetings | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  | 0 | bar: 2018 F to 2018 M
|  | 3 | Perform data consolidation, analysis and interpretation | 1 | District or area | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 600 |  |  |  | 0 | bar: 2018 A
|  | 4 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
|  | 5 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
| 2 |  | Packgaging of the State of the Cost Report (SCR) | 1 | SCR Report | 2655 | 1400 | 200 | 500 | 500 | 55 | 0 | 2655 | 2900 | 0 | 0 | 0 | 0 | bar: 2018 A to 2018 J
|  | 1 | Drafting of the SCR | 1 | SCR Report | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 700 |  |  |  | 0 | bar: 2018 A
|  | 2 | Conduct validation meetings on the biodiversity assessment results | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  | 0 | bar: 2018 A to 2018 M
|  | 3 | Revision/editing, finalization of the SCR | 1 | SCR Report | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 300 |  |  |  | 0 | bar: 2018 M
|  | 4 | Publication of the SCR | 50 | copies | 5 | 0 | 0 | 0 | 0 | 5 |  | 5 | 250 |  |  |  | 0 | bar: 2018 J
7 |  |  | State of the Cost Report available | 1 | SCR Report | 7005 | 3800 | 1100 | 1000 | 1000 | 105 | 0 | 7005 | 7250 | 0 | 0 | 0 | 0 | bar: 2018 J
| 1 |  | Conduct of biodiversity assessment survey | 1 | SCR Report | 4350 | 2400 | 900 | 500 | 500 | 50 | 0 | 4350 | 4350 | 0 | 0 | 0 | 0 | bar: 2018 J to 2018 A
|  | 1 | Conduct data collection and occular inspection | 1 | District or area | 2100 | 1400 | 700 | 0 | 0 | 0 | 0 | 2100 | 2100 |  |  |  | 0 | bar: 2018 J to 2018 M
|  | 2 | Conduct consultation meetings | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  | 0 | bar: 2018 F to 2018 M
|  | 3 | Perform data consolidation, analysis and interpretation | 1 | District or area | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 600 |  |  |  | 0 | bar: 2018 A
|  | 4 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
|  | 5 |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  | 0
| 2 |  | Packgaging of the State of the Cost Report (SCR) | 1 | SCR Report | 2655 | 1400 | 200 | 500 | 500 | 55 | 0 | 2655 | 2900 | 0 | 0 | 0 | 0 | bar: 2018 A to 2018 J
|  | 1 | Drafting of the SCR | 1 | SCR Report | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 700 |  |  |  | 0 | bar: 2018 A
|  | 2 | Conduct validation meetings on the biodiversity assessment results | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  | 0 | bar: 2018 A to 2018 M
|  | 3 | Revision/editing, finalization of the SCR | 1 | SCR Report | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 300 |  |  |  | 0 | bar: 2018 M
|  | 4 | Publication of the SCR | 50 | copies | 5 | 0 | 0 | 0 | 0 | 5 |  | 5 | 250 |  |  |  | 0 | bar: 2018 J
|  |  | Grand Total |  |  |  | 25200 | 7500 | 6500 | 6500 | 680 | 0 | 46380 | 47850 | 0 | 0 | 0 | 0

## Dashboard
Status of Implementation
Date Updated: |  | 2018-06-10
Project Facts
| Project Facts | Quantity
| Component | 3
| Output | 9
| Major Activities | 26
| Sub-activities | 33
Outputs Produced
| Component | Number of Outputs | Completed | Ongoing | Not Yet Started
| Component 1 | 5 | 1 | 2 | 2
| Component 2 | 6 | 2 | 4 | 0
| Component 3 | #REF! | #REF! | #REF! | #REF!
| Component 4 | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
| Component | Number of Major Activities | Completed | Ongoing | Not Yet Started
| Component 1 | 9 | 3 | 2 | 4
| Component 2 | 9 | 7 | 2 | 0
| Component 3 | 3 | 1 | 2 | 0
| Component 4 | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
4
Project Summary:
4 Components
9 Coutcomes
18 Outputs
42 Activities

## Multi-Year_IndicatorTracking
Achievement of Results
Project Title: IW R2R Project in Tuvalu
Implementing Partner: Ministry of Home Affairs & Rural Development
Implementation Period: August 2019 to March 2020
Update as of: |  | 2018-05-27
Updated by: |  | ______________________________
Code | Project Component/ Objective Statement |  | Indicator | Baseline | Target End of Project | End of Project Target | End of Target Balance (Column G-(Column R) | Annual Planned Targets |  |  |  |  | Summary of the Actual Annual Achievements (As reported in the PIR) |  |  |  |  | Means/Source of Verification | Risks and Assumptions | REMARKS Strategic Requirements and Conditions for successful implementation, risks and assmptions monitoring, etc.
[8 empty] | 2017 | 2018 | 2019 | 2020 | Total (Equal to End of Project Target) | 2017 | 2018 | 2019 | 2020 | Total Accumulated Accomplishment (Final Report)
Project Objective Level
[7 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Outcome | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1 | 1.1 Improved domestic pig pen operations catalysed via piloting of locally appropriate methods for on-site pig waste management ( target 50 pig pens) | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Output | 1.1.1 | 1.1.1 Appropriate onsite pig waste management piloted |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 1.1.2 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.2 | 1.2.1 Domestic pig waste managed and environmental impact contained | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Output | 1.2.1 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.3 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Output | 1.3.1 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 1.3.2 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
2.1 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Output | 2.1.1 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
2.2 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Output | 2.2.1 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 2.2.2. | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 2.2.3 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 2.2.4 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Outputs | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | 14 National pilot project area diagnostics based on R2R approach inclluding: baseline environmental state and social data incorporating CC vulnerabilities; and local governance of water, land, forests and coasts reviewed | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.2 | 14 national pilot projects test methods for catalizing local community action, utilizing and providing best practice examples, and building institutional linkages for integrated land, forest, water and coastal management | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Catchment level and coastal area integrated approaches (ICM/IWRM) introduced and/or scaled up in priority sites for 14 PICs | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
2.3 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Output | 2.3.1 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 2.3.2 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 2.3.3 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
3.1 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Output | 3.1.1 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 3.1.2 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 3.1.3 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
3.2 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Output | 3.2.1 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 3.2.2 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
3.3 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Output | 3.3.1 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 3.3.2 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 3.3.3 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | Reports on visits undertaken, both progress reports and those of participants | Demonstrable improved and results of best practices will only start to become evident towards the end of the project, including for LMMA, forest plantings and conservation farming/agroforestry practices
0
1
2

## MYCWP
Multi-Year Costed Work Plan
Project Title: IW R2R Project in Tuvalu
Implementing Partner: Ministry of Home Affairs & Rural Development
Implementation Period: August 2019 to March 2020
Version (Indicate the Date): August 02, 2019
Reference Code |  |  |  |  | Output/ Major activity/ Sub activity | Status | Quantity | Unit of Measure | Unit price | Detailed Components of the unit price | [13 empty] | Total Cost for the activity (Column H multiply with Column X) | Fund Sources | [30 empty] | Responsible Parties |  |  | REMARKS
Component | Outcome | Output | Major Activity | Sub-Activity | [5 empty] | 71200 | 71300 | 71400 | 71600 | 72100 | 72200 | 72400 | 72500 | 72800 | 73400 | 74100 | 74200 | 74500 | Subtotal Cost per unit |  | Government xxx | National IW R2R Project | STAR Project | PMU/SPC | Other 2 | Other 3 | Total Budget (in USD) | 2019 | [11 empty] | 2020
[10 empty] | International Consultants | Local Consultants | Contractual Services - Individuals | Travel on Office Business | Contractual Services - Companies | Equipment & furniture | Comm. and Audio Visual equipment | Supplies | Information technology equipment | Rental & Maintenance of other equipment | Professional Services | Audio Visual & Printing Production Costs | Miscellaneous expenses | [9 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Main/Lead | Support | Others
1 |  |  |  |  | 1. Demonstration of innovative approaches to pig waste management on Funafuti Atoll, Tuvalu | 1 |  |  | 0 | [13 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
| 1 |  |  |  | 1.1 Improved domestic pig pen operations catalysed via piloting of locally appropriate methods for on-site pig waste management ( target 50 pig pens) | 1 | [24 empty] | 0
|  | 1 |  |  | 1.1.1 Appropriate onsite pig waste management piloted | 1 | [24 empty] | 0
|  |  | 1 |  | 1.1.1.1 Assessment of Pig Waste impacts and management practices. | 2 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  | 1 |  | 1.1.1.2 Review pig waste management options, include cost considerations | 2 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  | 2 |  | Consult, design and construct X number of improved domestic pig pen. (dry litter) | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 1 | 1.1.1.3.1 Revisit specifications of the proposed pig pens in consult with PWD for a uniform design and costing for DLP Champions | 2 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 2 | 1.1.1.3.2 Seek fundings for the materials of the new improved pig pens | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 3 | 1.1.1.4.3 Procure and Construct the identified new improved pig pens | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
| 2 |  |  |  | 1.2 Environmental and public health safeguarded via targeted reductions in nutrient and pathogen contamination of coastal areas | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  | 1 |  |  | 1.2.1 Domestic pig waste managed and environmental impact contained | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  | 1 |  | 1.2.1.1 Assessment of baseline nutrient and pathogen loads from current pig waste management practices | 0 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 1 | 1.2.1.1.1 Identification of sites (pig pens) | 2 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 2 | 1.2.1.1.2 Collection of samples | 0 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 3 | 1.2.1.1.3 Analysis of data and report | 0 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  | 2 |  | 1.2.1.2 Monitoring program inititated with construction of improved domestic pig pen | 0 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 1 | 1.2.1.2.1 Preparation of programme to conduct monitoring | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 2 | 1.2.1.2.2 Execute the monitoring programme | 0 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  | 3 |  | 1.2.1.3 Assessment of reduction in nutrient and pathogen loads from improved domestic pig waste management practices | 0 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 1 | 1.2.1.3.1 Collect vital data from improved domestic pig waste management | 0 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 2 | 1.2.1.3.2 Analysis of data and report | 0 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
| 3 |  |  |  | 1.3 National uptake of sustainable pig waste management methods stimulated through community awareness and training | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  | 1 |  |  | 1.3.1 sustainable waste management enhanced through targeted engagement strategies | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  | 1 |  | 1.3.1.1 Review past and current community engagement regarding pollutant causes, impacts and control, and develop and deliver participatory enagement approaches | 0 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  | 2 |  | 1.3.1.2 review, develop and conduct community engagement approaches for the design, adoption and siting of sustainable pig waste management options | 2 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  | 3 |  | 1.3.1.3 review (existing/similar), develop and conduct technical trainings for construction and maintenace of sustainable pig waste management methods | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 1 | 1.3.1.3.1 Consult with experts in construction and evaluate the best alternatives | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 2 | 1.3.1.3.2 Formulate training manual and prepare for trainings | 0 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 3 | 1.3.1.3.3 Engage experts that may assist in conctruction and maintanence of sustainable pig waste management methods | 0 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
2 |  |  |  |  | 2. Targeted scientific approaches to optimise on-site waste management systems and to identify causal links between land-based contaminants and the degradation of coastal waters | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
| 1 |  |  |  | 2.1 Evidence based scaling up of eco-sanitation through optimal design and operation of systems to meet international standards for water safety and use of human compost in Tuvalu | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  | 2 |  |  | 2.1.1 Science based and community driven design and management of eco-sanitation (compost toilet) systems | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  | 1 |  | 2.1.1.1 current baseline data on community perceptions of eco-san, and nutrient and pathogen reduction, established and gaps identified through desktop review, including investigative data collection where necessary | 2 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 1 | 2.1.1.1.1 Conduct a survey on perceptions of eco-sanitation | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 2 | 2.1.1.1.2 Consult with authorities on the eco-saniation programmes | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 3 | 2.1.1.1.3 Prepare report for both ! & 2 | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  | 2 |  | 2.1.1.2 design and implement monitoring framework and develop a design assessment based on results of options. | 2 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 1 | 2.1.1.2.1 Implement monitoring programme that have been designed and to include community participation | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  | 3 |  | 2.1.1.3 Recommendations made to Project Management Group and adopted | 2 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 1 | 2.1.1.3.1 Compile findings (together with PCU) and propose recommnedations to Project Management Group. | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
| 3 |  |  |  | 2.2 Evidence based scaling up of dry-litter piggery systems through optimal design and operation of systems to meet international standards for water safety and use of animal compost in Tuvalu | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  | 1 |  |  | 2.2.1 Science based and community driven design and management of dry-litter piggery system | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  | 1 |  | 2.2.1.1 current baseline data on community perceptions of dry-litter piggeries, and nutrient and pathogen reduction established and gaps identified through desktop review, including investigative data collection where necessary | 2 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  | 2 |  | 2.2.1.2 design and implement monitoring framework and deveop a design assessment based on results of options. | 2 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 1 | 2.1.1.3.2 Implement monitoring programme that have been designed and to include community participation | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  | 3 |  | 2.2.1.3 Recommendations made to Project Management Group and adopted | 2 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 1 | 2.2.1.3.1Compile findings and propose recommnedations to Project Management Group. | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
| 2 |  |  |  | 2.3 Ecological health of lagoon waters of Funafuti Atoll are characterised and land-based contamination processes established for key ICM planning and investment | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  | 1 |  |  | 2.3.1 Ecosystem process monitoring programme established providing science based information | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  | 1 |  | 2.3.1.1 review and develop methodology for baseline and monitoring assessments of land-based contaminants, including identification of priority sites for implementation | 2 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 1 | 2.3.1.1.1 Identification of priority sites | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 2 | 2.3.1.1.2 Develop methodology for baseline and monitoring assesments of land based contaminants | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  | 2 |  | 2.3.1.2 implement monitoring programme, including community participation | 2 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 1 | 2.3.1.2.1 Engage with community to execute the initiative | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  | 3 |  | 2.3.1.3 Characterise ecological health of sites and report findings to Project Management Group and community - feedback to inform ongoing monitoring plans | 2 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 1 | 2.3.1.3.1 Compile and prepare report on findings to project management group | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
3 |  |  |  |  | 3. National and local capacity for waste management implementation built to enable best practice in coastal waters, land and public health protection | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
| 1 |  |  |  | 3.1 Volunteer waste management networks are formally established towards forming an enhanced culture of environmental protection in Tuvalu | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  | 1 |  |  | 3.1.1 National ICM Policy conserving coastal habitats through regulation of animal and human wastes | 1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [6 empty] | 0
|  |  | 1 |  | 3.1.1.1 Stakeholder consultation and development of network | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 1 | 3.1.1.1.1Conduct meetings and consultations with all stakeholders | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  | 2 |  | 3.1.1.2 outreach and training for network members, information exchange with wider community | 1 | 1 |  | 5538 | [12 empty] | 5538 | 5538 | 5538 |  | 5538 |  |  |  |  | 5538
|  |  |  | 1 | 3.1.1.2.1 Workshops and trainings to inform networks and communities | 0 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
| 2 |  |  |  | 3.2 Increased householder uptake of and donor support for on-site sanitation systems | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  | 1 |  |  | 3.2.1 Low cost waste management systems with sustainable options for financing provided | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  | 1 |  | 3.2.1.1 assess and identify options for reducing costs of implementing opitmised waste management systems | 2 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  | 2 |  | 3.2.1.2 identify potential sustainable financing options for communtiies and HH and develop roadmaps for financing | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 1 | 3.2.1.2.1 Engage with financial institutions and other possible donors | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 2 | 3.2.1.2.2 Prepare summary report on findings to finalise options | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  | 3 |  | 3.2.1.3 review, develop and conduct training for community and HH on accessing financing options. | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 1 | 3.2.1.3.1 Engage with memebrs and community to provide training on accesing funds | 0 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
| 3 |  |  |  | 3.3 Enhanced access to effective information relating to on-site waste management issues and linkages with environmental and public health to increase public awareness | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  | 1 |  |  | 3.3.1 Capacity for sustainable waste management approaches enhanced | 1 | [16 empty] | 0 | 0 | [6 empty] | 0
|  |  | 1 |  | 3.3.1.1 review available information (local and international) as it relates to waste management (DLT) and environmental/public health | 2 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 1 | 3.3.1.2 Using outcome from component 1 and 3.1.1 develop outreach and training materials | 0 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 2 | 3.3.1.3 identify and engage with media, design and publications partners | 0 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  | 2 |  | 3.3.1.4 Distribute materials through network outreach and other partners | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 1 | 3.3.1.2.1 Consult with relevant personnel with expetise (Tuvalu Media Corporation)) | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  |  | 2 | 3.3.1.2.2 Engage and execute the proposed strategy | 1 |  |  | 0 | [13 empty] | 0 | 0 | [6 empty] | 0
|  |  | 3 |  | 3.3.1.3 identify and engage with media, design and publications partners | 1 | 1 |  | 27881 |  | 8805 | [8 empty] | 10770 | 2115 | 6191 | 27881 | 27881 |  | 27881 |  |  |  |  | 27881
|  |  |  | 3 | [18 empty] | 0 | 0 |  | 0
[5 empty] | Salaries for Project Manager | 1 | 1 |  | 32400 |  |  | 32400 | [10 empty] | 32400 | 32400 |  | 32400 |  |  |  |  | 32400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | NPSC Meetings | 1 | 1 |  | 2000 | [12 empty] | 2000 | 2000 | 2000 |  | 2000 |  |  |  |  | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Sub-Total |  |  |  | 67819 | 0 | 8805 | 32400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10770 | 2115 | 13729 | 67819 | 67819 | 0 | 67819 | 0 | 0 | 0 | 0 | 67819
Summary Sub-activities |  |  |  |  | not yet started | 11 | 33.33%
[5 empty] | ongoing | 20 | 60.61%
[5 empty] | completed | 2 | 6.061%
[5 empty] | Total | 33 | 100%
Summary Major activities |  |  |  |  | not yet started | 4 | 15.38%
[5 empty] | ongoing | 8 | 30.77%
[5 empty] | completed | 14 | 53.85%
[5 empty] | Total | 26 | 100%
Summary Outputs |  |  |  |  | not yet started | 0 | 0%
[5 empty] | ongoing | 9 | 100%
[5 empty] | completed | 0 | 0%
[5 empty] | Total | 9 | 100%
Summary Outcomes |  |  |  |  | not yet started | 0 | 0%
[5 empty] | ongoing | 9 | 100%
[5 empty] | completed | 0 | 0%
[5 empty] | Total | 9 | 100%
Summary Components |  |  |  |  | not yet started | 0 | 0%
[5 empty] | ongoing | 3 | 100%
[5 empty] | completed | 0 | 0%
[5 empty] | Total | 3 | 100%
0
1
2

## Fiji (hidden)
Detailed Work and Financial Plan
Project Title: Implementing Ridge to Reef approach to preserve ecosystems services, sequester carbon, improve climate resilience and sustain livelihoods in Fiji
Implementing Partner: Ministry of Local Government, Housing and Environment
Implementation Period: March 2018 to March 2021 (4 years)
Version (Indicate the Date): March 13, 2018
Outcome |  |  |  | Output/ Major activity/ Sub activity | Status | Quantity | Unit of Measure | Unit price | Detailed components of the unit price | [6 empty] | Cost per output & activity | Fund Sources |  |  |  |  | Implementation Period | [47 empty] | Responsible Parties |  |  | REMARKS
| Outputs | Major Activity | Sub-Activity | [5 empty] | Personnel/ Consultant/s (Person x Daily Rate x Days) | Estimated Travel & Accomm Cost | Workshop venue | Food | Procurement or rental of Equipments, materials, publication, etc. | Others | Subtotal Cost per unit |  | National Government counterpart | STAR Project | Others 1 | Others 2 | Total Budget (in USD) | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021
[22 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Main/Lead | Support | Others
0 |  |  |  | Fij Project effectively managed. | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  |  | Personnel Cost | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 |  | Project Manager (Remuneration - Salary+Benefits) | 0 | 48 | Monthly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 |  | Finance Assistant (time allocation) | 0 | 48 | Monthly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 |  |  | 0
4
5
6
|  | 7 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 |  |  | Project operations | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 |  | Other Operational costs (office supplies, etc.) | 0 | 48 | Monthly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 |  | Office space | 0 | 48 | Monthly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 2018 Nov: 0; 2018 Dec: 0; 2019 Jan: 0; 2019 Feb: 0; 2019 Mar: 0; 2019 Apr: 0; 2019 May: 0; 2019 Jun: 0; 2019 Jul: 0; 2019 Aug: 0; 2019 Sept: 0; 2019 Oct: 0; 2019 Nov: 0; 2019 Dec: 0; 2021 Jan: 0; 2021 Feb: 0; 2021 Mar: 0; 2021 Apr: 0; 2021 May: 0; 2021 Jun: 0; 2021 Jul: 0; 2021 Aug: 0; 2021 Sept: 0; 2021 Oct: 0; 2021 Nov: 0; 2021 Dec: 0
|  | 3 |  | Utilities (water, electricity, communications) | 0 | 48 | Monthly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 |  | Attendance to Semi-Annual National Project Steering Committee Meetings | 0 | 8 | Meeting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5 | [5 empty] | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 6 | [5 empty] | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 2018 Nov: 0; 2018 Dec: 0; 2019 Jan: 0; 2019 Feb: 0; 2019 Mar: 0; 2019 Apr: 0; 2019 May: 0; 2019 Jun: 0; 2019 Jul: 0; 2019 Aug: 0; 2019 Sept: 0; 2019 Oct: 0; 2019 Nov: 0; 2019 Dec: 0; 2021 Jan: 0; 2021 Feb: 0; 2021 Mar: 0; 2021 Apr: 0; 2021 May: 0; 2021 Jun: 0; 2021 Jul: 0; 2021 Aug: 0; 2021 Sept: 0; 2021 Oct: 0; 2021 Nov: 0; 2021 Dec: 0
|  | 7 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 |  |  |  | Improved management effectiveness of existing and new protected areas | 0 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  |  | Expanded terrestrial and marine PA system: Three new terrestrial protected areas (Tunuloa, Tuva and Vunivia) delineated and formally established to conserve biodiversity, especially unprotected ecosystems and threatened species, and maintain ecosystem goods and services in an R2R context. One new MPA (Tuva) develop and incorporated into FLMMA. | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2018 Nov: 0; 2018 Dec: 0; 2019 Jan: 0; 2019 Feb: 0; 2019 Mar: 0; 2019 Apr: 0; 2019 May: 0; 2019 Jun: 0; 2019 Jul: 0; 2019 Aug: 0; 2019 Sept: 0; 2019 Oct: 0; 2019 Nov: 0; 2019 Dec: 0; 2021 Jan: 0; 2021 Feb: 0; 2021 Mar: 0; 2021 Apr: 0; 2021 May: 0; 2021 Jun: 0; 2021 Jul: 0; 2021 Aug: 0; 2021 Sept: 0; 2021 Oct: 0; 2021 Nov: 0; 2021 Dec: 0
1
2
3
4
|  | 2 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
2
3
4
|  | 3 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 | 2018 Aug: 0; 2018 Nov: 0; 2018 Dec: 0; 2019 Jan: 0; 2019 Feb: 0; 2019 Mar: 0; 2019 Apr: 0; 2019 May: 0; 2019 Jun: 0; 2019 Jul: 0; 2019 Aug: 0; 2019 Sept: 0; 2019 Oct: 0; 2019 Nov: 0; 2019 Dec: 0; 2021 Jan: 0; 2021 Feb: 0; 2021 Mar: 0; 2021 Apr: 0; 2021 May: 0; 2021 Jun: 0; 2021 Jul: 0; 2021 Aug: 0; 2021 Sept: 0; 2021 Oct: 0; 2021 Nov: 0; 2021 Dec: 0
1
2
3
4
4
1
2
3
4
5
1
2
3
4
6
1
2
3
4
7
1
2
3
4
| 2 |  |  | Improved Management of PA System: One existing terrestrial protected area (Sovi Basin) and six existing LMMAs/MPAs strengthened through development and/or implementation of management plans following the Community Conserved Areas (CCA)/LMMA approach to conserve biodiversity and maintain ecosystem goods and services in a R2R context. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
2 |  |  |  | Improved financial sustainability for terrestrial and marine protected area systems
| 1 |  |  | Valuation of biodiversity and other ecosystem services completed in at least two sites as basis for sustainable conservation finance approaches. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2018 Sept: 0; 2018 Nov: 0; 2018 Dec: 0; 2019 Jan: 0; 2019 Feb: 0; 2019 Mar: 0; 2019 Apr: 0; 2019 May: 0; 2019 Jun: 0; 2019 Jul: 0; 2019 Aug: 0; 2019 Sept: 0; 2019 Oct: 0; 2019 Nov: 0; 2019 Dec: 0; 2021 Jan: 0; 2021 Feb: 0; 2021 Mar: 0; 2021 Apr: 0; 2021 May: 0; 2021 Jun: 0; 2021 Jul: 0; 2021 Aug: 0; 2021 Sept: 0; 2021 Oct: 0; 2021 Nov: 0; 2021 Dec: 0
|  | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2018 Nov: 0; 2018 Dec: 0; 2019 Jan: 0; 2019 Feb: 0; 2019 Mar: 0; 2019 Apr: 0; 2019 May: 0; 2019 Jun: 0; 2019 Jul: 0; 2019 Aug: 0; 2019 Sept: 0; 2019 Oct: 0; 2019 Nov: 0; 2019 Dec: 0; 2021 Jan: 0; 2021 Feb: 0; 2021 Mar: 0; 2021 Apr: 0; 2021 May: 0; 2021 Jun: 0; 2021 Jul: 0; 2021 Aug: 0; 2021 Sept: 0; 2021 Oct: 0; 2021 Nov: 0; 2021 Dec: 0
|  | 2 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2018 Nov: 0; 2018 Dec: 0; 2019 Jan: 0; 2019 Feb: 0; 2019 Mar: 0; 2019 Apr: 0; 2019 May: 0; 2019 Jun: 0; 2019 Jul: 0; 2019 Aug: 0; 2019 Sept: 0; 2019 Oct: 0; 2019 Nov: 0; 2019 Dec: 0; 2021 Jan: 0; 2021 Feb: 0; 2021 Mar: 0; 2021 Apr: 0; 2021 May: 0; 2021 Jun: 0; 2021 Jul: 0; 2021 Aug: 0; 2021 Sept: 0; 2021 Oct: 0; 2021 Nov: 0; 2021 Dec: 0
4
5
6
7
| 2 |  |  | Review of user fee system and options for LMMA in Fiji, including development and implementation of user fee system for Tuva/Natadola. | 0 |  |  | 0 | [6 empty] | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 6 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 |  |  | Assessment completed on the existing Trust Fund for Sovi basin and potential for its utilization by planned new R2R PAs; guidelines for fund management and utilization reviewed and recommendations formulated. | 0 |  |  | 0 | [6 empty] | 0 | #REF! |  |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 |  |  | 0 |  |  | 0 | [6 empty] | 0 | #REF! |  |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 |  |  | 0
|  | 5 |  |  | 0
|  | 6 |  |  | 0
3 |  |  |  | Carbon stocks restored and enhanced in priority catchments | 0 |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  |  | Restoration and enhancement of carbon stocks in degraded forests in six priority water catchments using native tree species commencing with demonstration/research plots in each catchment. | 0 |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 6 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 7 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 |  |  | National sectoral policies strengthened with INRM (covering land, water, forests, biodiversity) in the following sectors: forestry, agriculture, lands, fisheries, iTaukei, tourism, and health. | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 |  |  | 0 |  |  | 0 | [6 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 |  |  | 0 |  |  | 0 | [6 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 |  |  | National and Provincial government - relevant agency staff including RokoTuis, Assistant Rokos and Conservation Officers, trained for INRM through leadership and/or participation in project activities. | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 6 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 7 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 |  |  | Empowered communities as a result of participation in: 1) formulation of PA management plans and catchment management plans; 2) alignment of community livelihoods with local priorities; 3) development of market-based instruments within the project, including ecosystem services. | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 6 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  |  |  | Improved data and information systems on biodiversity; land, forests, coastal and marine management; climate change and best practices | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  |  | Information portal established for easily accessible data and information on project outcomes based on biodiversity, forests, coasts, land and water management practices, including climate change. | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 |  |  | A knowledge management component is integrated into the ToR of all project staff to streamline information management process. | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 |  |  | A portal policy developed to guide the structure of the data and information received. | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 |  |  | 0 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 |  |  | 0 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 |  |  | 0
|  | 4 |  |  | 0
|  | 5 |  |  | 0
| 4 |  |  | A knowledge management officer is recruited to ensure that the data and information captured from project activities are catalogued, archived and maintained in a meaningful way. | 0
|  | 1 |  |  | 0
|  | 2 |  |  | 0
|  | 3 |  |  | 0
|  | 4 |  |  | 0
|  | 5 |  |  | 0
| 5 |  |  | Discoverability and accessibility of the projects information portal is ascertained and addressed. | 0
|  | 1 |  |  | 0
|  | 2 |  |  | 0
|  | 3 |  |  | 0
|  | 4 |  |  | 0
|  | 5 |  |  | 0
| 6 |  |  | Facilitate linkages with other relevant information portals in the region such as the Pacific Climate Change Portal, Disaster Net, University of the South Pacific Research Portal and the USP-EU GCCA knowledge center. | 0
|  | 1 |  |  | 0
|  | 2 |  |  | 0
|  | 3 |  |  | 0
|  | 4 |  |  | 0
|  | 5 |  |  | 0
| 7 |  |  | A communications strategy of the project Portal is designed and implemented so relevant partners are aware and can access information of the project from the portal. | 0
1
2
3
4
5
| 8 |  |  | Knowledge products (brochures, flyers, videos) on all thematic/focal areas and best practices developed and disseminated through various print and broadcast media.
1
2
3
4
5
| 9 |  |  | Exchange visits by community leaders, resource owners and farmers to observe catchment use and management (including best, good and bad practices).
1
2
3
4
5
National Project Management |  |  |  | State of the Cost Report available |  | 1 | SCR Report | 7005 | 3800 | 1100 | 1000 | 1000 | 105 | 0 | 7005 | 7250 | 0 | 0 |  | 0 | 0 | bar: 2018 Jun
|  | 1 |  | Conduct of biodiversity assessment survey |  | 1 | SCR Report | 4350 | 2400 | 900 | 500 | 500 | 50 | 0 | 4350 | 4350 | 0 | 0 |  | 0 | 0 | bar: 2018 Jan to 2018 Apr
|  |  | 1 | Conduct data collection and occular inspection |  | 1 | District or area | 2100 | 1400 | 700 | 0 | 0 | 0 | 0 | 2100 | 2100 |  |  |  |  | 0 | bar: 2018 Jan to 2018 Mar
|  |  | 2 | Conduct consultation meetings |  | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  |  | 0 | bar: 2018 Feb to 2018 Mar
|  |  | 3 | Perform data consolidation, analysis and interpretation |  | 1 | District or area | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 600 |  |  |  |  | 0 | bar: 2018 Apr
|  |  | 4 |  |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0
|  |  | 5 |  |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0
|  | 2 |  | Packgaging of the State of the Cost Report (SCR) |  | 1 | SCR Report | 2655 | 1400 | 200 | 500 | 500 | 55 | 0 | 2655 | 2900 | 0 | 0 |  | 0 | 0 | bar: 2018 Apr to 2018 Jun
|  |  | 1 | Drafting of the SCR |  | 1 | SCR Report | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 700 |  |  |  |  | 0 | bar: 2018 Apr
|  |  | 2 | Conduct validation meetings on the biodiversity assessment results |  | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  |  | 0 | bar: 2018 Apr to 2018 May
|  |  | 3 | Revision/editing, finalization of the SCR |  | 1 | SCR Report | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 300 |  |  |  |  | 0 | bar: 2018 May
|  |  | 4 | Publication of the SCR |  | 50 | copies | 5 | 0 | 0 | 0 | 0 | 5 |  | 5 | 250 |  |  |  |  | 0 | bar: 2018 Jun
|  |  |  | State of the Cost Report available |  | 1 | SCR Report | 7005 | 3800 | 1100 | 1000 | 1000 | 105 | 0 | 7005 | 7250 | 0 | 0 |  | 0 | 0 | bar: 2018 Jun
|  | 1 |  | Conduct of biodiversity assessment survey |  | 1 | SCR Report | 4350 | 2400 | 900 | 500 | 500 | 50 | 0 | 4350 | 4350 | 0 | 0 |  | 0 | 0 | bar: 2018 Jan to 2018 Apr
|  |  | 1 | Conduct data collection and occular inspection |  | 1 | District or area | 2100 | 1400 | 700 | 0 | 0 | 0 | 0 | 2100 | 2100 |  |  |  |  | 0 | bar: 2018 Jan to 2018 Mar
|  |  | 2 | Conduct consultation meetings |  | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  |  | 0 | bar: 2018 Feb to 2018 Mar
|  |  | 3 | Perform data consolidation, analysis and interpretation |  | 1 | District or area | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 600 |  |  |  |  | 0 | bar: 2018 Apr
|  |  | 4 |  |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0
|  |  | 5 |  |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0
|  | 2 |  | Packgaging of the State of the Cost Report (SCR) |  | 1 | SCR Report | 2655 | 1400 | 200 | 500 | 500 | 55 | 0 | 2655 | 2900 | 0 | 0 |  | 0 | 0 | bar: 2018 Apr to 2018 Jun
|  |  | 1 | Drafting of the SCR |  | 1 | SCR Report | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 700 |  |  |  |  | 0 | bar: 2018 Apr
|  |  | 2 | Conduct validation meetings on the biodiversity assessment results |  | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  |  | 0 | bar: 2018 Apr to 2018 May
|  |  | 3 | Revision/editing, finalization of the SCR |  | 1 | SCR Report | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 300 |  |  |  |  | 0 | bar: 2018 May
|  |  | 4 | Publication of the SCR |  | 50 | copies | 5 | 0 | 0 | 0 | 0 | 5 |  | 5 | 250 |  |  |  |  | 0 | bar: 2018 Jun
|  |  | 2 | Conduct validation meetings on the biodiversity assessment results |  | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  |  | 0 | bar: 2018 Apr to 2018 May
|  |  | 3 | Revision/editing, finalization of the SCR |  | 1 | SCR Report | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 300 |  |  |  |  | 0 | bar: 2018 May
|  |  | 4 | Publication of the SCR |  | 50 | copies | 5 | 0 | 0 | 0 | 0 | 5 |  | 5 | 250 |  |  |  |  | 0 | bar: 2018 Jun
Support from SPC |  |  |  | State of the Cost Report available |  | 1 | SCR Report | 7005 | 3800 | 1100 | 1000 | 1000 | 105 | 0 | 7005 | 7250 | 0 | 0 |  | 0 | 0 | bar: 2018 Jun
|  | 1 |  | Conduct of biodiversity assessment survey |  | 1 | SCR Report | 4350 | 2400 | 900 | 500 | 500 | 50 | 0 | 4350 | 4350 | 0 | 0 |  | 0 | 0 | bar: 2018 Jan to 2018 Apr
|  |  | 1 | Conduct data collection and occular inspection |  | 1 | District or area | 2100 | 1400 | 700 | 0 | 0 | 0 | 0 | 2100 | 2100 |  |  |  |  | 0 | bar: 2018 Jan to 2018 Mar
|  |  | 2 | Conduct consultation meetings |  | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  |  | 0 | bar: 2018 Feb to 2018 Mar
|  |  | 3 | Perform data consolidation, analysis and interpretation |  | 1 | District or area | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 600 |  |  |  |  | 0 | bar: 2018 Apr
|  |  | 4 |  |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0
|  |  | 5 |  |  |  |  | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0
|  | 2 |  | Packgaging of the State of the Cost Report (SCR) |  | 1 | SCR Report | 2655 | 1400 | 200 | 500 | 500 | 55 | 0 | 2655 | 2900 | 0 | 0 |  | 0 | 0 | bar: 2018 Apr to 2018 Jun
|  |  | 1 | Drafting of the SCR |  | 1 | SCR Report | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 700 |  |  |  |  | 0 | bar: 2018 Apr
|  |  | 2 | Conduct validation meetings on the biodiversity assessment results |  | 1 | Meeting | 1650 | 400 | 200 | 500 | 500 | 50 | 0 | 1650 | 1650 |  |  |  |  | 0 | bar: 2018 Apr to 2018 May
|  |  | 3 | Revision/editing, finalization of the SCR |  | 1 | SCR Report | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 300 |  |  |  |  | 0 | bar: 2018 May
|  |  | 4 | Publication of the SCR |  | 50 | copies | 5 | 0 | 0 | 0 | 0 | 5 |  | 5 | 250 |  |  |  |  | 0 | bar: 2018 Jun
|  |  |  | Grand Total | [11 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0
1
2
Note on R8: ADMIN: FSM Gov't promised to UNDP to have a counterpart of $560,474
Note on E64: ADMIN: validate what kind of support will be needed by the farmer cooperators to apply terrace farming practices
Note on E75: ADMIN: Ascertain what the practice will be